# Bosnia and Herzegovina

# Council of Ministers

### Semi-annual Review of the Action Plan for Realisation of the European Partnership Priorities

01 July 2009 – 31 December 2009

Directorate for European Integration

| Title: | Key Priorities |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Key priorities |  |  |  |  |  |  |  |  |  |
| Area: | Key priorities |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KLJP.001 | Adopt police reform legislation at State and Entity levels in line with the three EU principles and begin to implement the police reform | MS | Appoint Director of the Directorate for Coordination of Police Bodies | CoM | 0210 |  |  |  |  | Implementation of the activity was postponed from 1208 to 0210. Independent board for the nomination of the director of the police authorities has been designated and the vacant position for the director of the Directorate for coordination of police authorities has been announced. |
|  |  | MS | Appoint Director of the Agency for Education and Professional Development of Staff | CoM | 1209 |  |  |  |  | Implementation of the activity was postponed from 1208 to 1209. At its 78th session held on 26 February 2009, the Council of Ministers nominated the deputy director of the Agency for vocational education and training; however, the director of the Agency was nominated on 16 July 2009. |
|  |  | MS | Harmonise existing laws with 2 new laws on police reform | CoM | 1209 |  |  |  |  | Implementation of the activity was postponed from 1008 to 1209. The amendments to the following four laws have been adopted: Law on Ministries and other Administrative Authorities (dated 23 July 2009, Official Gazette no. 59/09), Law on Police Officers (dated 27 April 2009, Official Gazette no. 35/09), Law on State Investigation and Protection Agency (dated 18 June 2009, Official Gazette no. 49/09) and Law on Border Police (dated 13 July 2009, Official Gazette no. 59/09). |
|  |  | MS | Establish independent supervisory bodies (the Police Complaints Authority and Citizens Complaints Authority) | PABH | 1209 |  |  |  |  | Implementation of the activity was postponed from 1208 to 1209. The activity has been implemented, and the boards have been designated: Police officers’ Complaint Board (7 October 2008) and Citizens’ Complaint Board (14 September 2009). |
| EP3.KLJP.004 | Implement the 2006 strategy for public administration reform and ensure that State-level ministries and institutions are adequately financed, operational and properly equipped, especially in terms of premises and staff | PARCO | Improve efficiency and effectiveness of budget management (transparent public spending, involvement of managerial structures in preparations of a Budgetary Framework Document and the budget, introduction of programme budget proposals in BiH public administration, timely involvement of the Parliament in the budget adoption process, introduction of extensive reporting practice towards the Parliament and the public, better quality of the budget process in the FBiH) | FDBD MFC MFFBH MFRS MFT | 1211 |  |  |  |  | Implementation of the activity was postponed from 1209 to 1211. Transparency of expenditure has been ensured to the extent of 90 %. Institutions of BiH, RS and FBiH annually prepare the Programme of Public Investment. Management of the institutions has been partly involved in the development of the Document of Framework Budget and budget (managerial staff has been involved more than before). For the purpose of the budget preparation, consultations are held between the Sector for Budget and the managers of the budget institutions in August and September. Although some progress is evident, most of the budget institutions are rather represented by finance officers than by managers. Programme planning of the budget has been partly introduced. The amendments to the Law on financing BiH institutions have been adopted. The Law on amendments to the RS Law on Budget System has been adopted. Also, the Law on amendments to the Law on Budgets FBiH has been adopted. Budgets from 2011 and the Document of Framework Budget 2011-2013 will be included in programme budget. The parliaments have been timely involved in the budget allocation. The Law on amendments to the RS Law on Budget System has been adopted (Official Gazette no. 92/09); Brcko District Law on Budget is in place; FBiH Law on Budgets is in place; The amendments to the BiH Law on financing BiH institutions is in place (Official Gazette no. 49/09). The requirement of extended reporting to the parliament and public has been partly fulfilled. In BD, the template report for the Parliament has been developed, in RS the Law on Budget System stipulates that RS Finance Ministry shall submit quarterly reports on budget execution to the Government, and the Government shall semi-annually submit the reports on budget execution to the RS National Assembly. The Ministry of Finance and Treasury BiH launched the Rulebook on Reporting in 2007. |
|  |  | PARCO | Introduce the Public Internal Financial Control - PIFC in accordance with relevant EU standards (development of a strategy for introduction of the PIFC, the introduction of an internal audit function, the introduction of internal control, strengthening control environment) | FDBD HRUBD MFC MFFBH MFRS MFT | 1213 |  |  |  |  | Implementation of the activity was postponed from 1209 to 12/13. Working group for the development of PIFC Strategy finalised its work in 2009. The strategies were developed for the level of BiH, RS and FBiH. The Council of Ministers BiH (110th session, dated 30 December 2009) adopted the Strategy for implementation of public internal financial control in BiH institutions, whereby an SAA requirement was fulfilled. The Project Support to Introduction of Public Internal Financial Control (PIFC) in BiH will be financed from IPA 2007 programme, and the Project Support to Coordination of Capacities for Creation of Public Finance Policies and Management will be financed from IPA 2010 programme, the third component of which being Strengthening PIFC systems in BiH. |
|  |  | PARCO | Establish an efficient performance management system in the civil service to facilitate career development and increase staff motivation | CSA HRUBD MASGRS MJ | 0711 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 07/11. The implementation of the measure is planned through the project Development of the Performance Management System in Civil Service Structures of BiH that is financed from the Public administration reform fund and implemented at the level of BiH, FBiH, RS and Brčko District. Project operative implementation commenced on 4 January 2010 and will last through June 2011. Partial implementation of the measure was ensured through the existing regulation on civil service at administration levels and prior training and capacity building programmes (realisation of around 11% of the measure). By-law on assessment of civil servants is being prepared. Inter-department working group for the implementation of the Law on salaries and allowances in BiH institutions is to offer the proposal by-law that should define the issue of steps on the pay scale. |
|  |  | PARCO | Harmonise policies and establish common standards for probation work; establish the procedures and systems for introduction of new staff | CSA HRUBD MASGRS MJ | 0711 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 07/11. The implementation of the measure is planned through the project Development of the Performance Management System in Civil Service Structures of BiH that is financed from the Public administration reform fund and implemented at the level of BiH, FBiH, RS and Brčko District. Project operative implementation commenced on 4 January 2010 and will last through June 2011. Partial implementation of the measure was ensured through the existing regulation on civil service at administration levels and prior training and capacity building programmes (realisation of around 30 % of the measure). All recently recruited staffs undergo obligatory four-day long training. |
|  |  | PARCO | Establish disciplinary procedures and procedures for capacity building of managerial staff in the filed of modern human resource management policies | CSA HRUBD MASGRS PRB | 1209 |  |  |  |  | The implementation ensured through the detailed provisions of the by-laws at different levels of administration whereby the disciplinary procedures are regulated: Rulebook on disciplinary responsibility of civil servants in BiH institutions (Official Gazette BiH no. 20/03), Regulation on disciplinary procedure rules for disciplinary responsibility of civil servants in FBiH civil service authorities (Official Gazette FBiH no. 72/04 and 75/09 amendments), new Regulation on disciplinary and material responsibility in RS administrative authorities (Official Gazette of RS no. 104/09), Regulation on disciplinary and material responsibility of civil servants, government officers and employees in administrative authorities of BD BiH (2006). In addition, there exist the codes of ethics/conduct for civil servants (and other employees in administrative authorities) at the level of RS, FBiH and BD BiH, and the code of ethics is being prepared for BiH institutions. Managerial staff permanently undergoes training in the area of human resources management. 40 trainees underwent fortnight specialist training. |
|  |  | PARCO | Ensure that the members of the Complaint Review Board are familiar with basic principles of human resource management | CSA HRUBD MASGRS PRB | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. Partial implementation of the measure was ensured through the previous training and education programmes of the members of the civil service complaint board at the level of BiH, FBiH and RS (realisation of around 50%). Permanent follow-up of capacity building needs to be ensured for the civil service complaint board and Brčko District Appellate Committee. |
|  |  | PARCO | Apply good practices and, in cooperation with the civil service agencies and Sub-department for Human Resources of Brcko District, continually develop training programmes and procedures for managerial staff | CSA HRUBD MASGRS PRB | 1209 |  |  |  |  | Permanent obligatory training of the managers in civil service is being carried out – eight modules. |
|  |  | PARCO | Develop a manual on human resource policies in individual institutions and keep employees informed of their rights, duties and policy changes in the area of human resource management | CSA HRUBD | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. Partial implementation of the measure was ensured (realisation of around 50%). Within CSTP Project (Civil Servants Training Project), the guidelines were given for the development of the handbook for public sector institutions staff. In 2008, the magazine Modern Administration was launched in RS (the second edition published in 2009). In 2009, CSA RS issued the overview of the set of new laws on civil servants, Law on Government, RS administration and administrative inspection. Web page of CSA and Administrative Department of BiH Brcko District Government was created (In the third quarter of 2008 both in RS and FBiH, standardization and redesign of web page was done). Information available to the employees of civil service on web pages, notice boards and through regular communication of the institutions with the central units of the Office for Human Rights. Implementation of BH HRMIS (Human resources Management Information System in public administration of BiH) will ensure more complete implementation of the measure. |
|  |  | PARCO | Simplify the communication with media | AI CSA | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. Communication with media defined at the level of BiH, FBiH and RS by rulebooks and instructions on standard operative practices of the public relations officers. The list of media representatives who follow the work of the executive authorities has been drawn up at the level of BiH, FBiH and RS. Guidelines and principles of communication with media have not been drawn up in the Government of Brčko District where it is necessary to establish the central office for public relations within the Government. Managerial staff training has been envisaged for 2010. |
|  |  | PARCO | Develop and adopt a Public Administration Reform Action Plan 2 (AP2) | PARCO | 0611 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/11. PARCO is preparing the development of AP2. In September 2009, EUPAR project implementation commenced, and should result in the capacity development for the sectoral reforms and draft AP2. Within this project, cooperation with key institutions has been established and key documents identified. It is expected by April to have the methodology identified. Finalisation of AP2, establishment of implementation mechanisms and adoption of the document planned to be done by June 2011. |
| EP3.KLJP.005 | Strengthen administrative capacity in preparation for implementing Stabilisation and Association Agreement (SAA) and Interim Agreement (IA) commitments | DEI | Strengthen the Public Administration Reform Coordinator Office, both in terms of organisation and material resources | PARCO | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. By amendments of the Rulebook on internal organisation and systematisation, PARCO capacity has been strengthened in 2008 and 2009, and by granting it status of an independent budget beneficiary, its budget has been increased. By the end of 2007, PARCO started the activities to transform itself into a directorate in order to become the authority with appropriate authorisations and resources necessary for public administration reform coordination. On 10 December 2007, the Office of the Chairman of CoM submitted the request for providing the opinion about this proposal to the following: Ministry of Justice BiH, Ministry of Finance and Treasury BiH and Office for Legislation BiH and all these institutions provided their positive opinion. The plan and programme of the work of CoM for 2009 envisaged the change of status of PARCO; however, the measure being unfulfilled, it was included in the plan and programme of the work of CoM for 2010. |
| EP3.KLJP.006 | Pursue efforts aimed at reconciliation between citizens of the countries in the region and enhance efforts to find definitive solutions to pending bilateral issues, in particular border issues | MFA | Continue the process of final demarcation of border line between BiH and neighbouring countries Croatia, Serbia and Montenegro | MFA | 1209 |  |  |  |  | Through continued political dialogue in 2009, the Ministry of Foreign Affairs BiH, at political bilateral consultations with the representatives of foreign ministries of the Republic of Croatia, Republic of Serbia and Republic of Montenegro, introduced initiatives and underlined the need to engage in more intensive communication between the expert groups formed for the purpose of negotiation on open issues between BiH, Croatia and Serbia, as well as activities of all other government institutions responsible for resolving certain open and contested issues. Special attention was devoted to border issues and appointing of the meetings of state border commissions. The border commission of BiH and Montenegro made the best progress; they held two meetings in order to agree the text of the agreement and to prepare it for signing. |
| EP3.KLJP.008 | Reduce structural rigidities that distort the functioning of the labour market, in particular the taxation of labour, levels of social transfers and wage-setting mechanisms in order to increase the participation and employment rates | MCA | Organise a consultation process involving key experts and policy creation agencies at the state and entity level through the working groups which will assess the costs of measures targeting labour market | FMLSP LEA MCA MLVPRS | 1010 |  |  |  |  | Implementation of the activity was postponed from 09/09 to 10/10 in accordance with time limits planed for IPA 2007 project. |
|  |  | MCA | Identify legislative and other parameters focusing on key groups in respect of which the active labour market measures will be applied in cooperation with social partners from private and other sectors | FMLSP MCA MLVPRS | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10 in accordance with time limits planed for IPA 2007 project. |

| Title: | Political Criteria |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Democracy and the rule of law |  |  |  |  |  |  |  |  |  |
| Area: | Public administration |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.014 | Provide the Public Administration Coordinator’s Office with the human and material resources necessary to carry out its work | PARCO | Secure funding for the work of the Public Administration Reform Coordinator Office | CoM MFT PARCO | 1209 |  |  |  |  | As of 1 January 2008, the Office of the Coordinator became an independent budget beneficiary. The budget approved for 2009 amounts to 1,874,000 KM (in 2009, it was restructured because of the lack of funds for office rent). The budget approved by the Law on budget of the institutions and international commitments of BiH for 2010 amounts to 1,695,000 KM (Official Gazette BiH, no. 103/09) and suffices for work of the staff envisaged by the applicable Rulebook on internal organisation and systematisation. |
|  |  | PARCO | Amend the Rulebook on Internal Organisation of the Public Administration Reform Coordinator Office | PARCO | 0611 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/11. By the decision adopted by CoM on 24 April 2008, the Rulebook on amendments to the Rulebook on internal organisation and systematisation of the Office of Chairman of CoM was adopted, by introducing 15 job openings (establishment of the unit for material-finance and general affairs, systematisation of positions for the implementation of AP1, preparation of AP2 management of the Public administration reform fund). The Rulebook was amended for the second time by the decision of CoM (16 April 2009) – 6 intern positions were cancelled and 6 officer positions introduced - 5 officers in charge of the Public administration reform fund and 1 in charge of information technologies. One component of the EU Delegation PARCO assistance project (EUPAR) is the institutional support to PARCO that encompasses the capacity analysis and proposal for strengthening organisational structure, in accordance with the tasks envisaged in PAR Strategy. The proposal of the new amendment of the Rulebook will be prepared by June 2011. |
| EP3.KP.017 | Complete the merger of the State and Entity ombudsmen and ensure that the State -level office has the resources necessary to function properly | MHRR | Pass the Law on Cessation of the Ombudsman of Republika Srpska and the Transfer of Powers to the BiH Human Rights Ombudsman | MHRR PABH PARS | 0610 |  |  |  |  | Implementation of the activity was postponed from 09/08 to 06/10. At the continuation of its 23rd session, RS National Assembly adopted the Law on invalidity of the Law on Ombudsman RS, on 23rd December 2009. The Law was published in the Official Gazette RS, no.118/09. The Law stipulates that within 60 days from the date when the Law entered into force, the entity ombudsman shall cease to exist. |
| EP3.SP.127 | Implement the public administration reform and ensure its sustainability. Increase the capacity for progressive legal harmonisation and implementation of the acquis | PARCO | Develop an evaluation system and further develop the monitoring system | PARCO | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. EUPAR assistance project envisages the analysis of the monitoring mechanism and evaluation of the implementation of the measures from Action Plan 1 of the public administration reform. Based on this analysis, the proposal of the improved monitoring will be given and evaluation system developed (presently in early phase). |
|  |  | PARCO | Update (amend) the Public Administration Reform Action Plan - AP1 | PARCO | 0611 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/11. EUPAR assistance project envisages the pilot analysis of two or three out of six areas of the Action Plan 1 of the public administration reform, including the identification of bottlenecks in the implementation of the measures from AP1. The analysis will serve as a basis for updating AP1 in all areas. By the end of February 2011, the proposal of improved AP1 will be given and presented to the relevant authorities. |

| Title: | Political Criteria |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Democracy and the rule of law |  |  |  |  |  |  |  |  |  |
| Area: | Anti-corruption policy |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.024 | Ensure proper implementation of the law on conflict of interests | CEC | Harmonise by-laws with the Law on Law on Conflict of Interest in the Institutions of BiH | CEC PABH | 0909 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 09/09. The by-laws have been harmonised with the amendments to the Law on Conflict of Interests in BiH institutions in the given time limit. The new Law on Prevention of Conflict of Interest in BiH institutions is in the parliamentary procedure. |

| Title: | Political Criteria |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Human rights and protection of minorities |  |  |  |  |  |  |  |  |  |
| Area: | Human rights and protection of minorities |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.025 | Remove provisions on the death penalty from the Republika Srpska constitution | MHRR | Remove death penalty provisions from the Constitution of Republika Srpska | PARS | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. Amendments to the Constitution of Republika Srpska were adopted at the 28th session of the RS National Assembly, held on 10th March 2009 and are subject to the procedure before the Council of peoples of the RS National Assembly. |
| EP3.KP.028 | Strengthen the protection of the rights of women and children | MHRR | Establish a new composition of the Council for Children | MHRR | 0610 |  |  |  |  | Implementation of the activity was postponed from 10/08 to 06/10. The text of the Decision on formation of the Council for children has not been harmonised by the entity. Following its harmonisation, the Decision will be forwarded to the BiH Council of Ministers, and following its adoption, the new members of the BiH Council for children will be nominated. |
|  |  | MHRR | Develop a report on implementation of the Plan of Action for Children in BiH 2002-2010, for the period 2008-2010 | MHRR | 0909 |  |  |  |  | Implementation of the activity was postponed from 01/09 to 09/09. The periodic report BiH on implementation of the Convention on Children's Rights was adopted at the 105th session of CoM held on 18 November 2009. The report also covers the implementation of the Action Plan for children of BiH (2002-2010) for 2008 and 2009. At the same time, it is the second, third and fourth periodic report for BiH on implementation of the Convention on Children's Rights. It was agreed with UNICEF to develop the new Action Plan for children in 2010 for the period 2011-2014 wherein the reporting periods will be marked as to the implementation of the Action Plan. |
|  |  | MHRR | Mark the 16 days campaign dedicated to fight violence against women | GEA MHRR | 1109 | 2 |  |  |  | Within the 16-day long campaign opposing the violence against women that took place from 25 November to 10 December 2009, the Agency for Gender Equality held and supported a number of activities to emphasize the importance of the entire community in fighting violence against women and presented a part of the global activities for fighting violence. |
| EP3.KP.029 | Agree on a comprehensive penitentiary reform and ensure construction of a State level prison | MHRR | Harmonise the laws on execution of criminal sanctions of the Federation of Bosnia and Herzegovina, Republika Srpska and Brcko District of Bosnia and Herzegovina with the BiH Law regulating this subject matter | LSBD MJFBH MJRS | 1209 | 150 |  |  |  | Implementation of the activity was postponed from 12/08 to 12/09. The transitional and final provisions of BiH law provided for the obligation of harmonisation of the laws of entities and Brcko District of BiH with BiH law in the area of execution of criminal sanctions in order to fulfil the requirement of harmonisation of regulations in that area and establishment of the single standards, that is, rights and obligations of the persons in custody and persons in prison in the entire territory of BiH. At its 35th session, RS National Assembly adopted the proposal Law on execution of criminal sanctions of Republika Srpska that is harmonised with the relevant law of Bosnia and Herzegovina. Federation BiH has not completely harmonised its law with BiH law; it has been partly harmonised on the basis of the Decision of the High Representative for BiH who passed the Law on amendments to the Law on execution of criminal sanctions in the Federation BiH, that was published in the Official Gazette FBiH, no.12/09. |
|  |  | MHRR | Amend the BiH Law on Execution of Criminal Sanctions, Detention and Other Measures in order to allow the introduction of new European standards recommended to the Council of Europe’s member states in 2006 | MJ | 0709 | 100 | 100 |  |  | BiH adopted the Law on amendments to the BiH Law on execution of criminal sanctions, custody and other measures; it was published in the Official Gazette BiH no.37/09, |
|  |  | MHRR | Harmonise by-laws with the amendments made to the BiH Law regulating this subject matter | MJ | 1209 | 50 | 50 |  |  | The following by-laws have been adopted: Rulebook on criteria for committing the convicted persons to an institution to serve the imprisonment sentence, Rulebook on internal regulations of the institutions for serving sentence, custody or other measures, Rulebook on amendments to the rulebook on allowances and vacation of the prisoners serving imprisonment sentence in the institution for execution of criminal sanctions and other measures of BiH, Rulebook on allowances and vacation of the prisoners serving imprisonment sentence in the institution for execution of criminal sanctions and other measures of BiH, Decision on special bonus for the officers employed in the institutions for execution of criminal sanctions and other measures of BiH. The annotated text of the BiH Law on execution of criminal sanctions, custody and other measures has been drafted; the Agreement on accommodation and reimbursement of costs for execution of security measures that are pronounced in the criminal procedure has been adopted, as well as in the other procedure whereby the treatment measure is pronounced. The Second-instance Disciplinary Commission for conducting disciplinary procedure has been nominated because of the cases of violation of the official duty of the officers of the institutions as well as the Second-Instance Commission for Damage, i.e. for establishing material responsibility of an officer or employee of the institution at work or in connection with work. On 14 January 2010, the coordination body was formed for harmonisation of regulations in the area of execution of criminal sanctions in BiH. |
| EP3.SP.129 | Ensure that the national legislation is fully compatible with the European Convention for Human Rights | MHRR | Develop an anti-discrimination law of Bosnia and Herzegovina | GEA MHRR | 1209 | 10 |  |  |  | Implementation of the activity was postponed from 10/08 to 12/09. The Law on prevention of discrimination was adopted at the 82nd session of the Council of Ministers of BiH, held on 2 April 2009, following which it was adopted by the Parliament BiH on 23 July 2009, and published in the Official Gazette no. 59/09. |

| Title: | Political Criteria |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Regional issues and international obligations |  |  |  |  |  |  |  |  |  |
| Area: | Regional issues and international obligations |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.035 | Enhance cooperation with neighbouring countries, notably on cross-border cooperation, the fight against organised crime, trafficking and smuggling, judicial cooperation and border management | MFA | Establish an integrated border control system at international border crossing points | MS | 0709 |  |  |  |  | In order to implement the BiH Strategy for Integrated Border Management (IBM), the Council of Ministers has established the State Commission for Integrated Border Management in BiH whose members are directors of agencies included in the IBM Strategy (BP, ITA, PHPA, SFA, and VOBH) and representatives of the Ministry of Security. The Agreement on Cooperation between Institutions involved in the process of integrated management of the state border of Bosnia and Herzegovina was signed in Sarajevo on 23 September 2009. In 2009 the Border Police took a series of actions to implement the obligations under the BiH Strategy for Integrated Border Management (IBM). This is particularly evident in the establishment of the Joint Risk Analysis Centre whose members are representatives of all agencies involved in the IBM, in cooperation with other agencies in BiH and the countries of the region in the implementation of joint operational actions, in mounting of joint patrols with neighbouring countries and in joint training and further development of information systems in GP, especially the joint Migration Information System. |
|  |  | MFA | Assessment of needs for joint operations with neighbouring countries based on signed agreements | MS | 0709 |  |  |  |  | Through the international operational actions taken to prevent the organized crime of people smuggling, excellent cooperation with the police from neighbouring countries (Croatia, Serbia and Montenegro) and the police forces of Macedonia, Slovenia and Austria was established under the SECI Centre coordination. In accordance with the Agreement with the Republic of Croatia on Cooperation in Border Surveillance and Protocols signed, joint action plans of mixed patrols set up with the Republic of Croatia, which define procedures provided in the Agreement and Protocols, are implemented. With a view to implementing the Convention on Police Cooperation in SEE, the following protocols have been signed: with Serbia - on joint patrols and regular meetings between the border police at all levels, and with Montenegro - on regular meetings between the border police at all levels, joint patrols and work on joint border crossings. In accordance with these protocols BP officers conduct joint patrols with the competent police bodies along the borders of Serbia and Montenegro. |
|  |  | MFA | Organisation of joint police training | MS | 0709 |  |  |  |  | In the implementation of the Agreement on Cooperation in Border Surveillance and Protocols signed with the Republic of Croatia in 2009, the project on Capacity Building of BP and Croatian police mixed patrols was implemented. The project consisted of a series of joint training and practical exercises aimed at effectively combating cross-border organized crime and illegal migration and included 150 officers from BH BP and Croatian MUP each. In accordance with the Protocol on the implementation of joint patrols signed by the Ministry of Security of BiH and the Ministry of Internal Affairs and Public Administration of Montenegro, the first stage of training which included 20 border police officers from BiH and Montenegro each was finalized. Joint plans of joint patrols are made regularly at all levels by BiH BP and Border Police of the Republic of Serbia. In the bilateral cooperation with Montenegro and Serbia two courses of training of helmsmen from the Support and Control Unit were held by instructors from the United States. The courses were held in Bar and Zvornik for 10 border police officers. Within the DCAF Border Security Programme Working Group for Education and Training, the International Training Course for Station Commanders (ITCSC) and Regional Commanders (ADL) is being held, four representatives of BP participating in it. According to the plan, training will be continued in the next year. |
|  |  | MFA | Establish an efficient international communication and data exchange system, in particular with neighbouring countries | MS | 0709 |  |  |  |  | The Memorandum of Understanding on Establishing a System of Statistics Exchange of Illegal Migration and Participation in a Regional Early Warning System was signed by the competent police authorities of BiH, the Republic of Albania, the Republic of Croatia, the Republic of Macedonia, the Republic of Montenegro and the Republic of Serbia. BP was designated as a national contact point in BiH. BP regularly exchange statistics with police agencies of neighbouring countries, as required. A Working Agreement on the Establishment of Operational Cooperation between the Ministry of Security of BiH and FRONTEX was signed. BP has established cooperation with INTERPOL, EUROPOL and the SECI Centre, which is best reflected in information exchange, as well as in taking of international operational actions to suppress cross-border crime. |
|  |  | MFA | Establish procedures for joint border control and surveillance with neighbouring countries | MS | 0709 |  |  |  |  | Within the Geneva Centre for Democratic Control of Armed Forces (DCAF) Border Security Programme recommendations for the development of procedures for seven forms of cross-border police cooperation were made. The recommendations for the development of procedures are: national contact points, liaison officers, working on joint border crossings, joint centres, joint operations, joint patrols and joint meetings. These recommendations were made for border police forces in the region and they include the best EU and Schengen practices. Currently, BP is making an analysis of the procedures and bringing them in line with operational needs and EU standards. The Project for Blocking of Secondary Land Border Crossing Points between BiH and Croatia was completed. The project aimed at blocking of 118 points out of which 68 ones were blocked on the BiH side. Activities on the implementation of a similar project on the Border Crossing Points of the state border with Montenegro are under way. A Joint Commission established by the competent authorities of Bosnia and Herzegovina and Montenegro identified 44 secondary BCPs to block. Representatives of the BiH border police and Montenegro BP signed a joint Elaborate Paper on Blocking. An initiative for the formation of expert teams of BiH and Serbia, which will also identify secondary BCPs to block along the common border, was made. |
|  |  | MFA | Sign an agreement regulating property matters with the Republic of Serbia | MJ | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. The Ministry of Justice of Bosnia and Herzegovina has tried to initiate conclusion of the Agreement on Regulation of Property Relations with the Republic of Serbia on several occasions. However, the initiative was not accepted by the Republic of Serbia giving a reason for rejection that questions of ownership relations among the countries of former Yugoslavia are adequately regulated in the Agreement on Succession Issues. In July of 2009, at the request of the Ministry of Justice of BiH, Ministry of Foreign Affairs of BiH re-submitted this initiative to the competent Ministry of Serbia and submitted a draft agreement which was proposed by the BH side as a starting point for negotiations. However, the Republic of Serbia has not responded to this proposal yet. |
|  |  | MFA | Sign an agreement regulating property matters with the Republic of Montenegro | MJ | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. Bosnia and Herzegovina has tried to initiate conclusion of the Agreement on Regulation of Property Relations with the Republic of Montenegro on several occasions; however, the initiative was not accepted. |

| Title: | Economic criteria |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Economic criteria |  |  |  |  |  |  |  |  |  |
| Area: | Economic criteria |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.039 | Accelerate the privatisation process, with the objective of transferring 5-10% of the publicly owned capital to the private sector, with the Federation targeting the upper limit | DEP | Adopt a document “Policy of State-owned Capital Privatization in the Federation of Bosnia and Herzegovina with a Priority Investments Programme” | GFBH | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 12/10. |
|  |  | DEP | Adopt separate law or regulation on companies in strategic sectors (telecom operators) | GFBH | 1210 |  |  |  |  | Implementation of the activity was postponed from 03/09 to 12/10. In early 2009 the F BiH Government established an inter-ministerial working group for drafting the law on privatization of telecom operators (BH Telekom and HT Mostar). The group stopped working without any concrete results. |
| EP3.KP.043 | Ensure that the commercial courts function properly and, in particular, enhance the capacity of courts to process corporate bankruptcy/liquidation procedures more efficiently | DEP | Draft an Action Plan for improvement of the work of the Commercial Departments in the Courts | MJ | 0210 |  | 700 |  |  | Implementation of the activity was postponed from 12/09 to 02/10. Drafting of the Action Plan for the enhancement of commercial divisions in the courts has started. It will be an integral part of the revised Action Plan of the Justice Sector Reform Strategy in BiH. The Law on Amendments to the Law on Courts (Republika Srpska Official Gazette 116/09) set the date for beginning of commercial courts in the Republika Srpska on 1 May 2010. |
|  |  | DEP | Adopt recommendations in terms of optimal number of judges and judicial associates. Make an analysis of required number of judges and prosecutors. | HJPC | 1209 |  |  |  |  | HJPC has determined the optimal number of regular and additional judges in the courts in BiH. The implementation will ensue in coordination with the competent executive authorities. A review is being made, aiming to determine the optimal number of prosecutors. Determining the optimal number of judge’s associates in the courts will be done within the activities for the full resolution of their status. |
| EP3.KP.044 | Strengthen legal certainty for local and foreign economic operators and improve business environment | DEP | Align the BiH Law on Foreign Direct Investment with the recommendations from the RIA study | MoFTER | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. The Draft Law on Foreign Direct Investment has been referred to the Parliament and is up for its second reading in the House of Representatives of the Parliamentary Assembly of BiH. |
| EP3.SP.134 | Complete the privatisation process and liquidate the remaining loss-making publicly owned enterprises that cannot be sold | DEP | Establish the list of companies having negative capital as well as a list of loss making companies | APFBH | 1210 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 12/10. |
| EP3.SP.136 | Step up the unbundling of network industries in order to open up the electricity, gas and telecommunications markets to additional suppliers with a view to increasing competition and efficient allocation of resources | DEP | Draft and adopt the BiH Law on Gas | FMEMI MEEDRS MoFTER | 0610 | 50 |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. There is no agreement in the expert team about the basic principles of organization of the natural gas sector. |
|  |  | DEP | Establish an internal gas market institutions: the Regulator, the Transmission System Operator, gas distribution system operators in line with the BiH Law on Gas | FMEMI MEEDRS MoFTER | 0610 | 1000 | 1000 | 1000 |  | Implementation of the activity was postponed from 12/09 to 06/10. Regulator and operator of gas transportation system will be established by the BiH Law on Gas. Gas distribution system operators exist at the entity level. |
| EP3.SP.137 | Continue reforms in the areas of registration of property, enforcement of contracts, bankruptcy procedures, registration, taxation and licensing of businesses in order to improve the business environment and promote entrepreneurship. Eliminate overlapping regulations imposed by different levels of government and inter-entity double taxation for companies | DEP | Complete a legal framework required for optimal functioning of the land administration | LSBD MJ MJC MJFBH MJRS | 1209 |  |  |  |  | The legislative framework for the optimal functioning of land administration has been already determined by the 2003 Republika Srpska Law on the Land Books and the Law on Real Rights, which began to apply as of 1 January 2010. In 2009 the Republika Srpska Draft Law on the Land Books was adopted. The legislative framework for the optimal functioning of land administration has been determined by the 2003 Federation of BiH Law on Land Books (Federation of BiH Official Gazette No. 19/03). In 2009 the Federation of BiH Draft Law on Land Books Federation was agreed on and referred to the Federation Government and Parliament for adoption. |
|  |  | DEP | Draft the criteria and legislation regulating the number and status of employees in the land registry offices | LSBD MJ MJC MJFBH MJRS | 1209 |  |  |  |  | Required number and status of employees in the Land Registry Offices in the RS is determined by the act on systematization of basic courts with Land Registry Division. In the coming period, additional criteria will be set in accordance with the service standards of Land Registry Offices. The number and status of employees in the Land Registry Offices in the Federation of BiH have been determined the Rulebook that was enacted by the Federation Ministry of Justice (Federation of BiH Official Gazette, No. 75/09). |
|  |  | DEP | Adopt the Law on Immovables | MFRS | 1209 |  |  |  |  | The law was adopted and published in the RS Official Gazette, No. 110/08 and has been in force since 1 January 2010. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Free movement of goods |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.045 | Improve and implement the legal framework for standardisation, metrology, accreditation and certification of products to bring it into line with EU standards and best practice; further approximate technical regulations with those of the acquis; enhance the capacity of the quality infrastructure and institutions, and create the legal basis for conformity assessment procedures | MoFTER | Strengthen institutional capacity of the Ministry of Foreign Trade and Economic Relations in order to fulfill the EC’s requirements in terms of free movement of goods (establishing Internal Market Unit) | MoFTER | 1209 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 12/09. Envisaged establishment of an Internal Market Unit has been replaced by the idea of establishing two new departments: Department for Technical Regulations and Department for Conformity Assessment. The Department of Technical Regulations has not been staffed yet (1 incumbent out of 5 ones planned). |
|  |  | MoFTER | Adopt a Rule Book on recognition of documents and conformity marks issued abroad | MoFTER | 0310 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 03/10. |
|  |  | MoFTER | Adopt a Regulation on designation of conformity assessment bodies | MoFTER | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 12/10. No consent by the Republika Srpska Government for the implementation of this activitiy. |
|  |  | MoFTER | Adopt the Low Voltage Directive | MoFTER | 0909 | 15 |  |  |  | Implementation of the activity was postponed from 09/08 na 09/09. The order was published in the BiH Official Gazette No. 98/09 of 21 December 2009. |
|  |  | MoFTER | Adopt the Machinery Directive | MoFTER | 0909 | 15 |  |  |  | Implementation of the activity was postponed from 09/08 to 09/09. The order was adopted and referred to the BiH Official Gazette for publication on 22 December 2009. |
|  |  | MoFTER | Adopt the Electromagnetic Compatibility Directive | MoFTER | 0410 | 18 |  |  |  | Implementation of the activity was postponed from 09/08 to 04/10. The order was adopted at the 12th meeting of the Committee for Technical Regulations held on 26 December 2009. The Directorate for European Integration has given a positive opinion. The next step is its publication in the BiH Official Gazette. |
|  |  | MoFTER | Adopt the Lifts Directive | MCT MoFTER | 0410 | 18 |  |  |  | Implementation of the activity was postponed from 09/08 to 04/10. The order was adopted at the 12th meeting of the Committee for Technical Regulations held on 26 December 2009. The Directorate for European Integration has given a positive opinion. The next step is its publication in the BiH Official Gazette. |
|  |  | MoFTER | Adopt the Toys Safety Directive | MCA MoFTER | 1211 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 to 12/11. Transposition of the valid Order is under way. Referral into public debate will ensue in late May 2010. The Committee for Technical Regulation has made a decision to transpose the new EU Directive No. 2009/48/EC, which entered into force in EU in June 2009. This directive is mandatory as of July 2011. |
|  |  | MoFTER | Adopt the Non Automatic Weighing Instruments Directive | IM MoFTER | 1210 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 to 12/10. Transposition of the Order is under way. Referral into public debate will ensue in late March 2010. |
|  |  | MoFTER | Adopt the Appliances Burning Gaseous Fuels Directive | MoFTER | 1210 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 to 12/10. Transposition of the Order is under way. Referral into public debate will ensue in late March 2010. |
|  |  | MoFTER | Adopt the Pressure Equipment Directive | MoFTER | 1210 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 to 12/10. Transposition of the Order is under way. Referral into public debate will ensue in late April 2010. |
|  |  | MoFTER | Adopt the Personal Protective Equipment Directive | MCA MoFTER | 1210 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 na 12/10. Transposition of the Order is under way. Referral into public debate will ensue in late February 2010. |
|  |  | MoFTER | Adopt the Equipment Explosive Atmospheres Directive | MoFTER MS | 1210 | 10 | 20 |  |  | Implementation of the activity was postponed from 06/09 to 12/10. Transposition of the Order is under way. It was refered into public debate on 12 January 2010. |
|  |  | MoFTER | Implement Quality Management System in line with BAS EN ISO 9001:2000 standard | IS | 1209 |  | 10 |  |  | Established, documented, being applied and maintained and continually improves quality management system according to the standard BAS EN ISO 9001:2009. |
|  |  | MoFTER | Staffing of the BiH Accreditation Institute (BATA) through recruitment of 6 new employees. | BATA | 1209 | 99 | 148 |  |  | The activity has been finished. |
|  |  | MoFTER | Develop new accreditation schemes (medical laboratories, quality management systems, environmental management system, etc.) | BATA | 1210 | 20 | 80 |  |  | Implementation of the activity was postponed from 12/09 to 12/10. An accreditation scheme of quality management system has been developed. The development of other schemes is postponed for 2010. During the implementation of IPA-2007 project other accreditation schemes will be developed successively. |
| EP3.KP.046 | Ensure continuing progress in adopting European standards (ENs) | MoFTER | Raising the level of awareness of the BiH public regarding the importance and role of standardisation through seminars, workshops, media and other | IS RISMRS | 1209 |  |  |  |  | The activity is carried out continuously. Details can be found in annual reports on the work of the Standardization Institute. |
|  |  | MoFTER | Continuous adoption of the European standards | IS RISMRS | 1209 |  | 50 |  |  | Conditions have been provided (offices have been rented) with mandatory continuing upgrading and replacement of equipment as well as continuous designing of new software with the constant improvement and development of existing ones. |
| EP3.KP.047 | Establish an internal consultation and notification mechanism for new technical regulations prior to adoption of measures with an impact on trade | MoFTER | Establish a legal framework for an enquiry point in the BiH Standardisation Institute | IS | 1209 |  |  |  |  | An information center in the field of standardization has been established. The Institute has signed “Good Practice Code” for the preparation, adoption and application of standards under Annex 3 of the World Trade Organization Agreement on technical barriers to trade. |
|  |  | MoFTER | Establish contact points in BiH institutions and appoint contact persons from each institution aiming at ensuring communication with the BiH Standardisation Institute enquiry point | IM IS MCA MCT MJ MoFTER MS | 1211 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/11. Implementation of the activity has been planned through funding from IPA 2009 project. |
|  |  | MoFTER | Establish a single information system to connect institutions’ contact points with the BiH Standardisation Institute enquiry point | IS MoFTER | 1211 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/11. Implementation of the activity has been planned through funding from IPA 2009 project. |
| EP3.KP.048 | Ensure that the market surveillance agency is fully functioning and continue to take steps to establish a market surveillance structure responding to the requirements of the acquis on free movement of goods | MoFTER | Staffing and capacity building through recruitment of 5 civil servants and 1 employee | MSA | 1210 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 12/10. The Market Surveillance Agency has hired a civil servant due to limited funds in the 2009 budget. The implementation has been postponed for 2010 in accordance with the BiH Market Surveillance Strategy. |
|  |  | MoFTER | Adopt the Law amending the BiH Law on General Product Safety (implementation of the Dangerous Imitations Directive as well as improvement and more precise definition of certain formulation and parts of the Law) | MSA | 1209 |  |  |  |  | Implementation of the activity was postponed from 05/09 na 12/09. The Law on General Product Safety and the Law on Amendments to the Law on the BiH Market Surveillance (which is taken from Dangerous Imitation Directive) adopted and published in BiH Official Gazette No. 102/09). On proposal of the Market Surveillance Agency, at the 108th meeting held on 10 December 2009, the Council of Ministers adopted the Decision on Restrictions on the Marketing and Use of Phthalates in Toys and Childcare Articles (BiH Official Gazette No. 4/10) and the Decision on Ban on Products Containing the Biocide Dimethylfumarate To Be Placed or Made Available on the Market (BiH Official Gazette No. 3/10). |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Customs and taxation |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.055 | Further approximate customs and tax legislation and procedures with the acquis and ensure that the Bosnia and Herzegovina tariff is timely updated on the basis of the most recent Combined Nomenclature | MoFTER | Draft and adopt the following instructions: the Instruction on Customs Procedure in Postal Services, the Instruction on Outward Processing, the Instruction on Temporary Admission, the Instruction on Customs Control Procedure, the Instruction on Free Zones | ITA | 1209 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 12/09. The following instructions have been enacted and published: Instruction on Customs Procedures in Postal Traffic, External Clearance (Outward Processing) Instruction, Instruction on Free Zones, Instruction on Enforcement of the Procedure under Cover of TIR Carnet, Instruction on the Procedure of Approval of Road Vehicles and Containers for Transport of Goods with Identification Marks under TIR System; Instruction on Temporary Import has been design and Manual of Subsequent Customs Control has been drafted and harmonized with EU TACTA. A working version of the draft Instruction on Processing under Customs Control and the continuation of drafting will follow under the IPA project. |
|  |  | MoFTER | Adopt new instructions: the Instruction on Transit, the Instruction on Return of Exported Goods, Instruction on Customs Debt Repayment and Remission, Instruction on Simplified Customs Procedure, | ITA | 1209 |  |  |  |  | Instructions for simplified procedures have been enacted: Guidelines on Simplified Declaration Procedure of Goods on Incomplete Declaration, Guidelines on the Local Export Clearance Procedure and Instructions on Simplified Customs Procedures on the Invoice. The following simplified customs procedures were introduced: Instructions on Simplified Customs Procedures on the Basis of Invoice, Simplified Customs Procedure on Incomplete Declaration, the Local (Home) Export Clearance and Simplified Customs Procedures by Electronic Controller of Invoice As a Simplified Customs Declaration. Other guidelines will be the subject-matter of the IPA project, which will begin in the second half of the 2010 and according to activities schedule of this project. |
|  |  | MoFTER | Training of customs officers in the field of simplified procedures | ITA | 1209 |  |  |  |  | Customs officers (and business people) have been trained in simplified customs procedures. |
| EP3.KP.056 | Ensure that the legal framework for free zones is compatible with EU standards and guarantees adequate supervision of free zones | MoFTER | Adopt the Law amending the Law on Free Zones aimed at aligning with acquis | MoFTER | 1209 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 12/09. The law has been passed and published in BiH Official Gazette No. 99/09. |
|  |  | MoFTER | Adopt a Rule Book on free zones surveillance | MoFTER | 0310 |  |  |  |  | Implementation of the activity was postponed from 09/09 to 03/10. |
| EP3.KP.057 | Ensure proper implementation of rules of origin, including diagonal cumulation | MoFTER | Educate customs officers in the field of the rules of origin | ITA | 0909 |  |  |  |  | Implementation of the activity was postponed from 03/09 to 09/09. Courses of training were held in 2008 and then in February and June 2009. Courses of training of newly-employed civil servants were held in the period between 2 October and 3 November 2009. |
| EP3.KP.058 | Implement customs valuation rules in accordance with international standards and practices | MoFTER | Educate customs officers in the field of customs valuation | ITA | 0510 |  |  |  |  | Implementation of the activity was postponed from 03/09 to 05/10. Courses of training of customs officers in the rules of determining the customs value (Customs Valuation Rules) were not held in the planned period of time, because the ITA organized and conducted training of 194 newly-employed officers without working experience in October and November 2009. |
| EP3.KP.060 | Further improve the administrative capacity to implement customs and tax legislation and to fight against corruption, cross-border crime and fiscal evasion | MoFTER | Improve a qualification structure through recruitment of 200 additional employees with an university degree (graduated economists and lawyers) | ITA | 0709 |  |  |  |  | Implementation of the activity was postponed from 05/09 to 07/09. After having selected the most successful candidates the Indirect Taxation Authority employed 195 officers without working experience. Since 1 September 2009 179 incumbents have taken the positions and since 1 October 2009 16 incumbents with four-year university education have taken the positions. |
|  |  | MoFTER | Adopt a new Rule Book on systematisation and internal organisation in order to improve an administrative capacity regarding the law enforcement in the areas of customs and taxation including fiscal evasion, fighting corruption and cross border crime | ITA | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. The Draft Rulebook on Structure and Job Descriptions has been drafted and referred to the Board of Directors for approval. |
| EP3.KP.062 | Commit to the principles of the Code of Conduct for business taxation and ensure that new tax measures are in compliance with these principles | MoFTER | Apply a risk analysis module in the procedure of the indirect taxes taxpayers registration | ITA | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. In 2009 the new Rulebook on the Registration and Entry in a Single Register of Indirect Tax Payers, and new Instruction on the Registration and Entry in a Single Register of Indirect Tax Payers were not adopted. |
|  |  | MoFTER | Apply a risk analysis module for selection of the taxpayers audit | ITA | 1209 |  |  |  |  | The Risk Analysis Module for selection of taxpayers audit has been applying since 1 October 2008. Every month, on the basis of certain criteria, taxpayers are selected for a list of priority control, and the application has had satisfactory results so far. |
|  |  | MoFTER | Improve registration on the Single Register of Indirect Taxes Taxpayers in order to achieve faster and efficient registration | ITA | 1209 |  |  |  |  | By adopting the new Law on Excise Taxes in BiH, the number of data to be entered in the single register (warehouses of heating oil, warehouses of excise goods and production facilities) has increased, so that the drafting of the new Rulebook on the Registration and Entry in a Single Register of Indirect Tax Payers and Draft Instruction on Registration and Entry in a Single Register of Indirect Tax Payers is an attempt to accommodate the optimum solution to conduct this procedure in a quick and efficient manner. |
|  |  | MoFTER | Draft Rule Book amending the Rule Book on the implementation of the Law on Value Added Tax | ITA | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. The Draft Rulebook was referred to the Director’s Office for further procedure. The procedure has been halted because the enactment procedure of the Law on Amendments to the Law on VAT has been halted. |
| EP3.SP.142 | Improve the transparency and exchange of information within the region and with the EU in order to facilitate enforcement of measures preventing avoidance or evasion of taxes | MoFTER | Improve capacity and liability of an Operation centre for tactical support, advising, and executing operations at international level | ITA | 1209 |  |  |  |  | The Agreement on the Establishment of the Joint Center for State Border Related Risk Analysis has been signed. The agreement stipulates that the ITA should establish a local center that will support the joint center in ITA operation. |
|  |  | MoFTER | Appoint an officer in the Regional Office of the Southeast European Cooperative Initiative for combating transborder crime (SECI Centre) located in Bucharest | ITA | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. The appointment of an officer as a permanent member to the South-East European Cooperative Initiative (SECI Center) Regional Office based in Bucharest is underway. The Ministry of Security of BiH has received a letter with nomination of a representative of ITA to the Joint Cooperation Committee (JCC) of SECI Center in Bucharest. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Competition |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.063 | Improve existing anti-trust legislation in line with the requirements of the Stabilisation and Association Agreement and strengthen the administrative capacity of the Competition Council | CCBH | Adopt the Law amending the Law on competition in line with requirements arising from the Stabilisation and Association Agreement | CCBH MoFTER | 0909 |  |  |  |  | Implementation of the activity was postponed from 04/09 to 09/09. The Law was passed on 1 October 2009 and published in Official Gazette No. 80/09. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Public procurement |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.065 | Ensure that the single public procurement system functions properly and implement public procurement legislation and procedures. Continue developing administrative capacity | PPA | Align bylaws with the new Law on Public Procurement | PPA | 1210 |  |  |  |  | Implementation of the activity was postponed from 10/08 to 12/10. The new text of the Law on Public Procurement has not been passed by the Parliament. On 1 October 2009 the Instruction on the Preparation and Delivery of Records on the Contract Awards in Public Procurement Procedure under Chapter II and Chapter III of the Public Procurement Law was adopted and published in the BiH Official Gazette No. 81/09. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Intellectual property law |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.066 | Make the Institute for Intellectual Property fully operational so that it can carry out its tasks effectively and implement and enforce the current legal framework | IIP | Structurally and functionally organise the Institute for IPR of BIH and make the classification of posts | IIP | 0909 |  |  |  |  | Implementation of the activity was postponed from 03/09 to 09/09. At the 93rd meeting held on 2 July 2009 the Council of Ministers of BiH adopted the Development Strategy of the Intellectual Property Institute of Bosnia and Herzegovina (2009-2015). At the 104th meeting held on 12 November 2009 the Council of Ministers approved the Rulebook on Structure of the Institute. |
|  |  | IIP | Draft a Patent Law, a Trademark Law, an Industrial Design Act, and a Law on Protection of Geographical Indications | IIP | 0909 |  |  |  |  | The Law on Copyright and Related Rights and the Law on Collective Accomplishment of Copyright and Related Rights were adopted at the 108th meeting of the Council of Ministers held on 10 December 2009. Patent Law, Trademark Law, Law on the Indications of Geographic Origin, the Law on the Topography of Integrated Circuits and the Law on Industrial Design were adopted on the 111th meeting of the Council of Ministers of BiH held on 30 December 2009. |
| EP3.KP.067 | Prepare an action plan for building the necessary capacity to implement and enforce intellectual property laws, with particular focus on the need to provide specialised training for law enforcement bodies, judges, prosecutors and customs officials | IIP | Train the staff of the Institute in the field of the TRIPS and SAA requirements, including study trips as well as a preparation of leaflets, guidelines and manuals | IIP | 0909 |  |  |  |  | Staff of the Institute has been trained in Intellectual Property as a Modern Factor of Development, so has staff of institutions responsible for implementation of IPR (Indirect Taxation Authority (Customs), Market Inspection, the Investigation and Protection Agency etc.). The courses of training were held in Mostar, Brcko, Banja Luka and Sarajevo. In the period May - June 2009 a training round was held for the Institute staff in state institutions for intellectual property of Croatia, Serbia and Slovenia. |
|  |  | IIP | Redesign and improve web site by including relevant data on the IPR | IIP | 0809 |  |  |  |  | Implementation of the activity was postponed from 01/09 to 08/09. In July 2009 substantially redesigned and improved Web site of the Institute was officially posted. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Employment and social policies |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.069 | Further develop social inclusion and social protection policies | MCA | Elaborate data which could be used as a solid ground for initiation of further development of strategies for social inclusion, action plans and their evaluation | BHAS FMES GDB GFBH GRS MCA MECRS MFFBH MFRS MFT MLVPRS | 1210 |  |  |  |  | Implementation of the activity was postponed from 11/09 to 12/10. The Directorate for Economic Planning is responsible for coordination of Development Strategy of Social Inclusion at the state level. Objectives, priorities and measures are defined, while the Action Plan is currently being designed and activities are being defined. A working version of the 2010-2013 Employment Strategy in the RS has been submitted for consultation. This strategy includes social inclusion policies. The 2010-2013 Employment Strategy in the F BiH was adopted on 28 September 2009 by F BiH Parliament. |
|  |  | MCA | Elaborate and implement all sectoral action plans within the framework of the state Poverty Reduction and Social Inclusion Strategy | BHAS GDB GFBH GRS MCA MECRS MFFBH MFRS MFT MLVPRS | 0610 |  |  |  |  | Implementation of the activity was postponed from 11/09 to 06/10. The Strategy for Equalization of Opportunities for Persons with Disabilities in F BiH and 2010-2014 Action Plan for the Government of F BiH were prepared. The measures under the Strategy for Poverty Reduction and Social Inclusion in the Republika Srpska have been implemented. Action plans are being designed and working groups are being appointed. |
|  |  | MCA | Enable greater participation of persons at risk of falling into poverty in decision making process with regards to decision having impact on their life | BHAS FMES GDB GFBH GRS MCA MECRS MFFBH MFRS MFT MLVPRS | 1210 |  |  |  |  | Implementation of the activity was postponed from 11/09 to 12/10. The Social Inclusion Strategy envisages mechanisms for greater participation of persons at risk of social exclusion in the processes of social actions. |
|  |  | MCA | Allow access to information and communication technologies | DEP FMLSP GDB GFBH GRS MCA MFFBH MFRS MFT MLVPRS | 1109 |  |  |  |  | The Strategy for Improving the Social Status of Persons with Disabilities in the Republika Srpska defines activities related to achievement of this goal. |
|  |  | MCA | Adopt a state level disability policy | DEP FMLSP GDB GFBH GRS MCA MFFBH MFRS MFT MLVPRS | 1109 |  |  |  |  | The Policy Paper on Disability in BiH has been adopted by the Council of Ministers. |
| EP3.KP.070 | Develop mechanisms for a social dialogue | MCA | Draft recommendations with regards to institutional arrangements needed for engagement of social partners in different areas | FMLSP MCA MLVPRS | 0910 |  |  |  | IPA 2007 | Implementation of the activity was postponed from 09/09 to 09/10 in accordance with the deadlines set in IPA 2007 Project. |
|  |  | MCA | Carry out the training on European integration and social dialog related issues, employment strategy, social dialog skills development | FMLSP LEA MCA MLVPRS | 1010 |  |  |  | IPA 2007 | Implementation of the activity was postponed from 10/09 to 10/10 in accordance with the deadlines set in IPA 2007 Project. |
|  |  | MCA | Draft an action plan for development of social dialog | FMLSP LEA MCA MLVPRS | 1110 |  |  |  | IPA 2007 | Implementation of the activity was postponed from 11/09 to 11/10 in accordance with the deadlines set in IPA 2007 Project. |
|  |  | MCA | Set up mechanisms which will contribute to tripartite cooperation between the governments and social partners with the purpose of establishing the Economic and Social Council | MCA MFT | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 06/10. In July 2009 a consultative meeting, which was related to the elimination of interference in the establishment of Economic and Social Council of BiH and the definition of proposals for the identification of representative partners to participate in the Economic and Social Council of Bosnia and Herzegovina, was held with representatives of all social partners. |
|  |  | MCA | Adopt the legislation regulating the establishment and organization of the state level Economic and Social Council | MCA MFT | 1010 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 10/10. After appointment of members of the Economic and Social Council of BiH, a working group composed of the appointed members, that would work on determining the text of the Agreement on Economic and Social Council of Bosnia and Herzegovina, with a special emphasis on the responsibilities of Council of Ministers and future competencies of Economic and Social Council BHP, will be established. |
| EP3.KP.071 | Make further efforts improve the situation of persons with disabilities | MCA | Planning of education system for persons with disabilities and adjustment of the lifelong learning systems | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 1109 |  |  |  |  | The Law on Vocational Rehabilitation, Training and Employment of Persons with Disabilities in the F BiH has been adopted. The Law on Vocational Rehabilitation and Employment of Disabled Persons (Republika Srpska Official Gazette No. 98/04 and 91/06) provides for employment of persons to work with disabled persons. |
|  |  | MCA | Establish services employing persons with disabilities in order to enable them to acquire economic independence | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 1109 |  |  |  |  | The Law on Vocational Rehabilitation, Training and Employment of Persons with Disabilities in the F BiH has been adopted. The Law on Vocational Rehabilitation and Employment of Disabled Persons (Republika Srpska Official Gazette No. 98/04 and 91/06) provides for employment of persons to work with disabled persons. |
|  |  | MCA | Develop a single institutional model for assessment of the degree of disability and remaining abilities of all persons with disabilities | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 0610 |  |  |  |  | Implementation of the activity was postponed from 11/09 to 06/10. The work-ability evaluation model for people with disabilities in accordance with the ICF classification is being designed in the Republika Srpska. The Law on the Establishment of the Institute for Medical Expert Evaluation of Health Condition in the F BiH has been passed. |
|  |  | MCA | Continue deinstitutionalisations and activities at the community level aiming at helping those in need through the Project “Support to BiH Disability Policy Development” | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 0610 |  |  |  |  | Implementation of the activity was postponed from 11/09 to 06/10. The Law on Amendments to the Law on Fundamentals of Social Welfare, Protection of Civilian Victims of War and Protection of Families with Children in the F BiH has been passed, the first drafts of the Law on Fundamental Rights of People with Disabilities and the Law on the Protection of Civilian Victims of War in the F BiH have been prepared and adopted by the FBiH Government and referred to the F BiH Parliament. The Republika Srpska is implementing the activity. |
|  |  | MCA | Removing different kinds of barriers | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 1109 |  |  |  |  | The Law on Vocational Rehabilitation and Employment of Disabled Persons (Republika Srpska Official Gazette No. 98/04 and 91/06) guarantees equality. |
|  |  | MCA | Ensure an equal access to the legal procedures | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 1109 |  |  |  |  | The activity has been implemented. There is no discrimination in access to legal proceedings. |
|  |  | MCA | Rise public awareness on importance of removing barriers such as prejudices, attitudes and stigma | FMES FMLSP GFBH GRS MCA MECRS MLVPRS | 0610 |  |  |  |  | Implementation of the activity was postponed from 1109 to 0610. The implementation is under way. |
| EP3.KP.072 | Develop adequate administrative structures and capacity in the field of consumer and health protection | MCA | Approximate national legislation in the field of consumer protection with acquis | MCA MoFTER | 0710 |  |  |  | Sredstva Fonda GTZ | Implementation of the activity was postponed from 12/09 to 07/10. Two laws in the field of consumer protection: the Law on Amendments to the Law on Consumer Protection and the Law on Fraudulent Advertising are in preparation. The deadline for submission to the Council of Ministers of BiH is June 2010. |
| EP3.SP.146 | In the area of mental health, develop community-based services as an alternative to institutionalisation, taking into account allocation of sufficient financial resources for mental health care | MCA | Adopt mental health policies and Action Plan for F BiH | FMH | 1210 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. The mental health policy is adopted at the level of the Federation Ministry of Health. The Action Plan is under construction and will be implemented jointly with the Swiss Agency for Development. |
|  |  | MCA | Establish a regional centre for mental health in the BiH | FMH GDB MCA MHSPRS | 0210 |  |  |  |  | Implementation of the activity is postponed from 1208 to 0210. Waiting for official confirmation of the World Health Organization on acceptance of the application for establishment of the Regional Center for Mental Health. |
|  |  | MCA | Amend the F BiH Law on Health Care and Health Insurance in the terms of strengthening community mental health services | FMH | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. In accordance with the conclusions of both Houses of the Parliament of the Federation of BiH, the public debate on the draft Law on Health Protection was conducted in the reporting period. Presently expected is the opinion of the Health Care Committee of the F BiH Parliament House of Representatives on the public debate, as well as the adoption of the final report on the part of the F BiH Parliament House of Representatives, which would provide a basis for preparation of the second phase of this law. It is important to note that this is a new Federation law in this area, so that, upon final sublimation of objections to this law, the first draft of the Law on Health Insurance will be passed on to the cantons. In fact, it is the proposed legal solutions in the Draft Law on Health Protection that the legal solutions in the first draft of the Law on Health Insurance will depend on. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | Education and research |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.073 | Implement the State level Law on higher education, paving the way for implementation of the main components of the Bologna process and the Lisbon Recognition Convention | MCA | Set up a clear and transparent criteria for accreditation of higher education institutions | MCA | 0710 |  |  |  |  | Implementation of the activity is postponed from 0909 to 0710. The Agency for Development of Higher Education and Quality Assurance prepared the proposal of the Criteria for Accreditation of Higher Education Institutions in BiH, which shall, in accordance with the work program of the Agency for 2010, be the subject of consultation with experts of the Council of Europe (February 2010), higher education institutions and relevant ministries (March-April 2010), and be adopted in the period of June-July 2010. godine. |
|  |  | MCA | Set up a criteria for choosing national as well as international quality assessment and evaluation experts | MCA | 0809 |  |  |  |  | The criteria for selection of domestic and international experts have been established and are published in the document titled Decision on Criteria forza izbor domaćih i međunarodnih stručnjaka koji daju ocjenu i obavljaju reviziju kvaliteta i daju preporuke o akreditaciji visokoškolskih ustanova i studijskih programa. Selection of Domestic and International Experts to Provide Assessment and Conduct Quality Reviews and Give Recommendations on Accreditation of Higher Education Institutions and Study Programs. The Decision was published in the “Official Gazette of BiH” No. 88/09 from November 10th 2009. Based on the Decision, the Agency for Development of Higher Education and Quality Assurance announced a public competition for selection of experts on December 14th 2009. |
|  |  | MCA | Register the Quality Assurance and Higher Education Development Agency in the European Quality Assurance Register as well as include the Agency into quality assurance network | CoM MCA | 0610 |  |  |  | IPA 2007 | Implementation of the activity is postponed from 1208 to 0610. The ECTS System (European Credit Transfer System) was introduced at all public universities in BiH. In accordance with the Decision of the BiH Council of Ministers No.108/08, Vijeće ministara BiH učlanjeno je u Evropski registar agencija za osiguranje kvaliteta visokog obrazovanja (EQAR). 108/08, the Council of Ministers became a member of the European Quality Assurance Register for Higher Education (EQAR) Odlukom Vijeca ministara BiH br.. The State Agency for Development of Higher Education and Quality Assurance is preparing for the membership in EQAR. In accordance with the Decision of the BiH Council of Ministers from its 105th session, the Agency for Development of Higher Education and Quality Assurance is authorized to initiate procedures for its membership in international, European and regional associations for quality assurance in the area of higher education and to represent Bosnia and Herzegovina in such associations for quality assurance. The funding for annual membership fees for 2009 godinu bit će osigurana restrukturiranjem budžeta Agencije za 2009. will be provided through restructuring of the Agency budget for 2009godinu, a nadalje će biti planirana godišnjim budžetom Agencije., and will in future be planned in the annual budget of the Agency. |
|  |  | MCA | Make an analysis of the situation at universities regarding transfer to integrated university model and recommendations for establishing of such model | MCA | 0611 |  |  |  |  | Implementation of the activity is postponed from 0909 to 0611. Initiated is the EU project "Support to Reform of Higher Education in BiH", financed from the IPA 2007 funds, and aimed at functional strengthening of the Center for Information and Recognition of Documents in the Area of Higher Education (CIP), as well as at addressing of the issues that should be regulated by the law on recognition of diplomas, preparing of the model of the integrated university in BiH, and giving of further recommendations for strengthening of the integrated university. The planned project duration is 24 months. |
|  |  | MCA | Establish an institutional structure and a budgetary regime of the BiH Rectors’ Conference | MCA | 0610 |  |  |  | IPA 2008 | Implementation of the activity is postponed from 1209 to 0610. |
| EP3.KP.074 | Resolve fragmentation of the educational system and the overlap of functions between different levels of organisation. Strengthen policy development and strategic planning to improve the quality of education | MCA | Establish the General Education Council | GDB MCA | 0610 |  |  |  |  | Implementation of the activity is postponed from 1208 to 0610. The Commission for Selection of Members of the BiH Council for General Education was formed in late March 2009, and it carried out the nomination procedure and compiled a list of proposed members of the Council, which was discussed by the Conference of Ministers of Education of BiH at its 10thSjednici održanoj 17.11.2009. Session held on November 17th 2009 in Sarajevo, but the proposal was not supported. In accordance with the conclusion of the Conference of Ministers of Education of BiH, the new Commission was formed, which began working in December 2009, and thegodine započela svoj rad i procedura izbora članova Vijeća je u toku. procedure of selection of Council members is in progress. |
| EP3.KP.075 | Take measures to prevent segregation of children along ethnic lines at school | MCA | Ministry of Civil Affairs of BiH shall draft the recommendations for overcoming a phenomenon of “two schools under one roof”, through the Conference of Education Ministers | MCA | 0610 |  |  |  |  | Implementation of the activity is postponed from 0109 to 0610. At the 9th sjednici Konferencije ministara obrazovanja u BiH, održanoj 29. Session of the Conference of Ministers of Education of BiH, held on September 29th 2009 in Banja Luka, the report of the Working Group for analysis of the phenomenon of "two schools under one roof” was supported with additional suggestions and recommendations made at the Session. At the same Session, the Conference of Ministers of Education of BiH agreed to form the new Working Group that will be headed by a representative of the OSCE, its members being representatives of the Federation Ministry of Education and Science, Ministries of Education of the Herzegovina-Neretva Canton, Zenica-Doboj Canton and Central Bosnia Canton, as well as representatives of the Council of Europe and the BiH Ministry of Civil Affairs, with a view to redefining the concept of "two schools under one roof." The Ministers of Education concluded that certain progress has been made in elimination of the phenomena of segregation and discrimination in education in BiH, but that such steps forward are not sufficient, and they urged the wider community, especially the parents and school boards to get involved in resolving of these problems. The Working Group has held one meeting to date.Ministri obrazovanja su konstatovali da je napravljen određeni napredak u eliminisanju pojava segregacije i diskriminacije u obrazovanju u BiH, ali da ti iskoraci nisu dovoljni, te su pozvali širu društvenu zajednicu, posebno roditelje i školske odbore da se uključe u rješavanje ovih problema. |
| EP3.SP.147 | Take measures to improve the education system, including primary education, and to create a modern vocational education and training system | MCA | Establishing standards of knowledge and assessment in preschool, primary and secondary education | GDB MCA | 1209 |  |  |  |  | The Agencies for Standards and Assessment of the Federation of BiH and Republika Srpska have established the standards of knowledge and grading for mother tongue and mathematics for individual classes of the primary school and general secondary school. In accordance with the Law on Agency for Preschool, Primary and Secondary Education, the Agency for Preschool, Primary and Secondary Education was established as the legal successor of the Agency for Standards and Assessment in Education for the Federation of BiH and Republika Srpska. The Law on Agency clearly stipulates that the Agency for Preschool, Primary and Secondary Education is competent to establish standards of knowledge and grading for preschool, primary and secondary education. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Internal market |  |  |  |  |  |  |  |  |  |
| Area: | WTO issues |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.078 | Continue the reforms necessary to comply with WTO rules and obligations and continue the work towards achieving WTO accession | MoFTER | Conclude bilateral negotiations on the market access including negotiations on customs concessions as well as negotiations on the market access in the field of trade in services | MoFTER | 1209 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. In March and October 2009godine održana su dva kruga bilateralnih pregovora o pristupu tržištu. two rounds of bilateral negotiations on market access were held. The negotiations have not been concluded. |
|  |  | MoFTER | Conclude multilateral negotiations on domestic support for agriculture | MoFTER | 1209 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. Agodine održan je plurilateralnui sastanak, au oktobru tri bilateralna sastanka sa SAD, Kanadom i Australijom. Pregovori nisu završeni. plurilateral meeting was held in March 2009, whereas in October 2009 three bilateral meetings were organized with the USA, Canada and Australia. The negotiations have not been concluded. |
|  |  | MoFTER | Align legislation with the WTO rules and principles | MoFTER | 1209 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. A round of negotiations was held in March 2009godine održan krug pregovora.. In October 2009 a set of documents was submitted for the next round, which is planned to take place in the first quarter of 2010. godine. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Agriculture and fisheries |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.084 | Ensure adoption of legislation compliant with the European standards in the food safety, veterinary and phytosanitary sectors and start to implement it | AFS MoFTER | Draft state level regulations for quality assurance of meat and meat products | AFS MoFTER PHPA VOBH | 1210 |  | 80 |  |  | Implementation of the activity is postponed from 1209 to 1210. |
|  |  | AFS MoFTER | Draft state level regulations for quality assurance of organic products | AFS MoFTER PHPA VOBH | 1211 |  | 80 |  |  | Implementation of the activity is postponed from 1209 to 1211. There is no regulation providing for quality assurance of organic products at the state level. RS has the Law on Organic Food Production (“Official Gazette of RS” No. 75/04 and 71/09), based on which the Rulebook on Conditions for Issuing of Certificates for Organic Products (“Official Gazette of RS” No. 113/08) was adopted. The Law on Organic Food Production in the Federation of BiH is in the final stage of preparation in the Federation Ministry of Agriculture, Water Management and Forestry. The activities aimed at harmonization of entity regulations will be carried forward to 2011. |
|  |  | AFS MoFTER | Adopt the Animal Waste Law | AFWDBD MAFWFBH MAFWRS VOBH | 1210 |  | 80 |  |  | Implementation of the activity is postponed from 1009 to 1210. The draft law was prepared by the State Veterinary Office in BiH and submitted to the entities for opinion. The veterinary services department of the RS Ministry of Agriculture, Forestry and Water Management (MAFW) stated the opinion that it is unconstitutional. |
|  |  | AFS MoFTER | Adopt the Animal Feed Law | AFWDBD MAFWFBH MAFWRS VOBH | 1210 |  |  |  |  | Implementation of the activity is postponed from 1009 to 1210. The provisions of this regulation are built in the new BiH draft Law on Veterinary Medicine. |
|  |  | AFS MoFTER | Adopt the Veterinary Drugs Law | AFWDBD MAFWFBH MAFWRS VOBH | 1210 |  | 20 |  |  | Implementation of the activity is postponed from 1009 to 1210. The draft law was prepared by the State Veterinary Office in BiH and submitted to the entities for opinion. The RS MAFW veterinary services department stated the opinion that it is unconstitutional. |
|  |  | AFS MoFTER | Amend the BiH Law on Veterinary | AFWDBD MAFWFBH MAFWRS VOBH | 1210 |  | 80 |  |  | Implementation of the activity is postponed from 1009 to 1210. The draft law was prepared by the State Veterinary Office in BiH and submitted to the entities for opinion. The RS MAFW veterinary services department stated the opinion that it is unconstitutional. |
|  |  | AFS MoFTER | Adopt a BiH regulation in accordance with the Council Directive 69/464/EEC on control of Potato Wart Disease (Synchytrium endobioticum) 31969L0464 | PHPA | 0809 |  |  |  |  | Activity implemented ("Official Gazette of BiH" No. 78/09). |
|  |  | AFS MoFTER | Adopt a BiH regulation in accordance with the Council Directive 69/465/EEC on control of Potato Cyst Eelworm (Heterodera rostochiensis) (31969L0465) | PHPA | 0809 |  |  |  |  | Implementation of the activity was postponed from 0609 to 0809. Activity implemented ("Official Gazette of BiH" No. 78/09). |
|  |  | AFS MoFTER | Adopt a BiH regulation in accordance with the Council Directive 93/85/EEC on the control of potato ring rot (Clavibacter michiganensis ssp. sepedonicus) (31993L0085), amended by the Commission Directive 2006/56/EC (32006L0056) | PHPA | 0809 |  |  |  |  | Implementation of the activity was postponed from 0609 to 0809. Activity implemented ("Official Gazette of BiH" No. 90/09). |
|  |  | AFS MoFTER | Adopt a BiH regulation in accordance with the Council Directive 98/57/EC on the control of Ralstonia solanacearum (Smith) Yabuuchi et al. (Ralstonia solanacearum) (31998L0057), amended by Commission Directive 2006/63/EC (32006L0063) | PHPA | 0809 |  |  |  |  | Implementation of the activity was postponed from 0609 to 0809. Activity implemented ("Official Gazette of BiH" No. 90/09). |
|  |  | AFS MoFTER | Draft a regulation on entry points in accordance with the Commission Directive 98/22/EC from 15 April 1998 (31998L0022) | PHPA | 0810 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1208 to 0810. |
|  |  | AFS MoFTER | Draft a regulation on minimum requirements for control of plants, plant products and other regulated items at entry points | PHPA | 0810 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1208 to 0810. |
|  |  | AFS MoFTER | Draft a regulation on procedures for preventing the introduction and spread of organisms harmful to plants, plant products and other regulated items | PHPA | 0810 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1208 to 0810. The Rulebook is separated into two parts. The Rulebook on the Lists of Harmful Organisms, Lists of Plants and Plant Products and Regulated Facilities is adopted and published in the Official Gazette of BiH No. 69/09, whereas the Rulebook on Measures for Prevention of the Introduction and Spread of Organisms Harmful to Plants, Plant Products and Other Regulated Articles is submitted for opinion. |
|  |  | AFS MoFTER | Draft a regulation on public call procedure for the authorisation of laboratories | PHPA | 0810 |  |  |  |  | Implementation of the activity is postponed from 0609 to 0810. The Regulation on Procedures for Announcement of Public Competitions/Advertisements for Authorization of Laboratories is in the phase of preparation. |
|  |  | AFS MoFTER | Draft a regulation on registration of owners (producers and importers) of certain types of plants, plant products and other regulated items in accordance with the Commission directives | PHPA | 0910 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1208 to 0910. The draft rulebook is in the consultation phase. |
|  |  | AFS MoFTER | Draft a regulation laying down the staff, equipment and infrastructure requirements for laboratories which carry out laboratory analyses and testing | PHPA | 0810 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 0609 to 0810. The draft Regulation on Defining of the Conditions in Terms of Personnel, Equipment and Infrastructure to be fulfilled by laboratories in order to conduct laboratory analyses and testing is in the phase of preparation. |
|  |  | AFS MoFTER | Copy of Potpuno kadrovsko osposobljavanje Uprave BiH za zaštitu zdravlja bilja | PHPA | 0611 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1209 to 0611. Implementation of the activity is planned through the IPA 2008 project. |
|  |  | AFS MoFTER | Draft a regulation on issuing plant passports at BiH level, based on Directive 92/105/EEC (31992L0105), amended by Directive 2005 /17/EC (32005L0017) | PHPA | 0810 |  |  |  | IPA2008+WB credit | Implementation of the activity is postponed from 1208 to 0810. The draft Regulation is in the phase of consultation. |
|  |  | AFS MoFTER | Complete staffing of BiH Phytosanitary Office | PHPA | 1209 |  | 600 |  | IPA2008+WB credit | The administrative capacity of the Plant Health Protection Administration (PHPA) includes 11 full time employees, 9 civil servants and 2 employees. |
|  |  | AFS MoFTER | Based on the Law on Seeds and Propagating Material of Agricultural Plants, draft BiH regulations on List of Varieties; regulations on Registration of Seeds, the Rulebook on Licensing in BiH; regulation on rights of plant varieties breeders | PHPA | 1210 |  |  |  | IPA 2008 | Implementation of the activity is postponed from 1209 to 1210. Draft regulations are under construction. |
|  |  | AFS MoFTER | Align the BiH Law on Phytopharmaceutical Products with the Council Directive 91/414/EEC concerning the placing of plant protection products on the market (31991L0414) | PHPA | 1210 |  |  |  | IPA 2008 | Implementation of the activity is postponed from 1209 to 1210. Harmonization of the Law is planned in 2010. The following regulations have been adopted: Decision on Banning of Registration, Import and Trade of Active Substances and Phytopharmaceutical Products Containing Active Substances whose Trade is Banned in the EU (Official Gazette of BiH No. 47/09), and the Rulebook on Handling of the Stocks of Plant Protection Products whose Trade and Use is Banned.(Sl.glasnik BiH 58/09). Ostali pravilnici u fazi izrade. (Official Gazette of BiH No. 58/09). Other rulebooks are in the preparation phase. |
|  |  | AFS MoFTER | Develop a training plan in the phytosanitary field | AFWDBD MAFWFBH MAFWRS PHPA | 0610 |  |  |  | IPA2008 | Implementation of the activity is postponed from 1208 to 0610. |
|  |  | AFS MoFTER | Draft detailed by-laws pertaining to the Law on Mineral Fertilizers, in particular those referring to import | PHPA | 1209 |  |  |  | IPA2008 | Adopted is the Rulebook on Conditions for Putting into Circulation, Quality and Quality Control of Mineral Fertilizers and the Storage and Handling of Mineral Fertilizers (Official Gazette of BiH No. 90/09). |
|  |  | AFS MoFTER | Draft a regulation on requirements for appointment of phytosanitary inspectors | PHPA | 0610 |  |  |  |  | Implementation of the activity is postponed from 0609 to 0610. |
|  |  | AFS MoFTER | Draft 30 rulebooks based on the Law on Food Safety | AFS | 1209 |  |  |  | IPA2007+WBcredit | Adopted and published are 9 rulebooks (Official Gazette of BiH No. 37/09, 39/09, 43/09): Rulebook on Honey and Other Bee Products; Rulebook on Methods for Control of Honey and Other Bee Products; Rulebook on Maximum Permitted Levels for Certain Contaminants in Food; Rulebook on Methods of Sampling and Analysis for the Official Control of the Levels of Lead, Cadmium, Mercury, Inorganic Tin, 3-Monochloro-propane- diol (3-MPCD) and Benzo(a)pyrene in Food; Rulebook on Methods of Sampling and Analysis for the Official Control of the Levels of Dioxins and Polychlorized Biphenyls similar to Dioxins in Food; Rulebook on Methods of Sampling and Analysis for the Official Control of Nitrate Levels in Food; Rulebook on Methods of Sampling and Analysis for the Official Control of the Levels of Mycotoxins in Food; Rulebook on Salt for Human Consumption; Rulebook on Conditions to Be Met by Authorized Testing Laboratories Conducting Food Analyses and on Laboratory Accreditation Procedure. The 14 rulebooks in the area of food were drafted and consequently adopted at the 113th Session of the Council of Ministers from January 21st 2010., Their publishing is expected in the Official Gazette of BiH. The drafts of the so-called Hygiene package are completed - 4 Rulebooks by the BIH Agency for Food Safety (AFS): Rulebook on Food Hygiene, Rulebook on Hygiene of Food of Animal Origin, Rulebook on Official Controls and Rulebook on Official Controls of Food of Animal Origin. |
|  |  | AFS MoFTER | Complete the staffing of BiH Food Safety Agency | AFS | 1209 |  | 440 |  | IPA2007+WBcredit | The Agency was in July 2009 staffed with additional 8 civil servants. Implementation of the project of strengthening of the capacity in food safety in BiH (IPA 2007) began in September 2009. In accordance with the Decision of the BiH Council of Ministers reached upon the proposal of the Agency, the Council for Genetically Modified Organisms (which is crucial for the implementation of the Law on GMOs adopted in March 2009) was appointed. |
|  |  | AFS MoFTER | Develop the plan for transposition of the EU veterinary regulations into BiH legislation | VOBH | 1209 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1209. The Plan for transposition of legislation in the field of veterinary medicine is prepared. |
| EP3.KP.085 | Enhance laboratory and inspection capacity in the food safety, veterinary and phytosanitary sectors, establish reference laboratories and develop sampling procedures in compliance with EU requirements | MoFTER | Enhance reference laboratories | AFS PHPA VOBH | 1210 |  |  |  | WBcredit | Implementation of the activity is postponed from 0609 to 1210. Through the IPA project the funds were approved for the purchase of laboratory equipment (LC/MS/MS and GC/MS/MS) for control of the hygienic safety of animal origin products (residue of veterinary drugs and other contaminants), which will be used to equip some of the veterinary laboratories. |
|  |  | MoFTER | Establish reference laboratories in the phytosanitary area | PHPA | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The activity is planned in the PHPA work program for 2010. |
|  |  | MoFTER | Set up a phytosanitary registry | PHPA | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The activity is planned in the PHPA work program for 2010. |
|  |  | MoFTER | Carry out intensive training of staff employed in inspectorates of Entities and Brčko District in order to facilitate the implementation of the hygiene package, as well as the verification and monitoring of the Hazard Analysis Critical Control Points system - HACCP | AFS | 1209 |  |  |  | IPA2007 | In cooperation with the TAIEX instrument, on December 4th 2008god.organizovan je uspješan seminar za 60 inspektora (svih nivoa vlasti) iz oblasti nadzora nad sigurnošcu u svrhu implementacije higijenskog paketa te verifikacije i nadzora HACCP sistema. a successful seminar was organized for 60 inspectors (from all levels of authority) in the area of supervision of safety aimed at implementation of the hygiene package, as well as verification and supervision of the HACCP system. |
|  |  | MoFTER | Carry out intensive training of staff employed in authorised laboratories | AFS | 1210 |  |  |  | IPA2007 | Implementation of the activity is postponed from 1209 to 1210. The activity is planned within the IPA 2007 project. |
|  |  | MoFTER | Create and procure a sophisticated information system (hardware/software) for risk assessments | AFWDBD MAFWFBH MAFWRS | 0611 |  |  |  | WBcredit | Implementation of the activity is postponed from 1209 to 0611. The deadline was extended after adoption of the decision on granting of authorization to laboratories for food control by the BiH Council of Ministers. |
| EP3.SP.153 | Implement the comprehensive State level agricultural strategy throughout the whole country | MoFTER | Adopt the Decision on Establishment of Farms and Customer Registry | MoFTER | 1210 |  |  |  | IPA2007+WBcredit | Implementation of the activity is postponed from 1209 to 1210. The Decision on Establishing of the Register of Farms and Clients was adopted and published in the Official Gazette of BiH No. 85/07. The MoFTER plan stipulates the adoption of a new decision harmonized with the Framework Law on Agriculture. |
|  |  | MoFTER | Adopt the Decision on Establishment of Agricultural Market Information Service | MoFTER | 0909 |  |  |  | IPA2007+WBcredit | Implementation of the activity was postponed from 1208 to 0909. The Decision on Establishing of the Agricultural Market Information Service of Bosnia and Herzegovina was published in the Official Gazette of BiH, No. 68/09. |
|  |  | MoFTER | Adopt regulation on administrative work for an agricultural pilot census | MoFTER | 1210 |  |  |  | IPA2007+WBcredit | Implementation of the activity is postponed from 0609 to 1210. The activity will be implemented with the assistance of the EU project "Strengthening and Harmonization of the BiH Information System for the Sectors of Agriculture and Rural Development" from the IPA 2007 (initiated on September 15th 2009) and in cooperation with the BiH Agency for Statistics. The preparations for implementation of the Pilot Agriculture Census are ongoing. The first meeting of the Working Group, when the work on methodological approach for conducting of the census will begin is planned to take place in January 2010. |
|  |  | MoFTER | Develop a Strategy for advisory bodies | MoFTER | 0510 |  |  |  | IPA2007+WBcredit | Implementation of the activity is postponed from 1208 to 0510. As a part of the ARDP (Agricultural Rural Development Project) project, a consultant is hired providing support to entities in development of harmonized strategies. The development of the strategy for RS and the Federation is in the final phase. TheOčekuje se konačno usvajanje do kraja maja 2010. final adoption is expected by the end of May 2010. The drafts were completed in January 2010.godine, nacrti su završeni u januaru 2010. |
|  |  | MoFTER | Procure equipment for advisory bodies | MoFTER | 0310 |  |  |  | IPA2007+WBcredit | Implementation of the activity is postponed from 1209 to 0310. The procurement of equipment for advisory service departments is planned to take place from thegodine iz sredstava ARDP (Agricultural Rural Development Project) projekta, odnosno po usvajanju harmoniziranih entitetskih strategija za savjetodavne službe. funds of the ARDP (Agricultural Rural Development Project) project in the first quarter of 2010 that is after the adoption of harmonized entity strategies for advisory service departments. In Republika Srpska this activity is ongoing. |
| EP3.SP.154 | Further strengthen the State level capacity for coordination and harmonisation of agricultural, food and rural development policy, reinforce implementation mechanisms and further approximate with the acquis | MoFTER | Strengthen/establish state level capacities for sectoral policies analysis | MoFTER | 1209 |  |  |  | IPA2008+IPA2009+WB | Implementation of the activity was postponed from 0609 to 1209. According to the new systematization of the BiH MoFTER, the Department for Policy Analysis, Monitoring, Evaluation and Information was established. In 2009 it employed 5 servants. The total number of employees in the Sector for Agriculture, Food, Forestry and Rural Development is 26. |
|  |  | MoFTER | Strengthen/establish state level capacities for coordination of human resources management | MoFTER | 1209 |  |  |  | IPA2008+IPA2009+WB | According to the new systematization of the BiH MoFTER, the Department for Policy Analysis, Monitoring, Evaluation and Information was established. In 2009 it employed 5 servants. The total number of employees in the Sector for Agriculture, Food, Forestry and Rural Development is 26. |
|  |  | MoFTER | Strengthen/establish state level capacities for awareness rising/public relations and information | MoFTER | 1209 |  |  |  | IPA2008+IPA2009+WB | According to the new systematization of the BiH MoFTER, the Department for Policy Analysis, Monitoring, Evaluation and Information was established. In 2009 it employed 5 servants. The total number of employees in the Sector for Agriculture, Food, Forestry and Rural Development is 26. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Environment |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.089 | Ratify and start implementing relevant international conventions, including the Aarhus and Espoo Conventions | MoFTER | Finalise the Espoo Convention ratification procedure | FMET GDB MAFWFBH MAFWRS MoFTER MPCERS | 1209 |  |  |  |  | Implementation of the activity was postponed from 0609 to 1209. The ratification procedure is completed for the ESPOO and Aarhus Conventions. |
|  |  | MoFTER | Identify structures for implementation of the Aarhus Convention | FMET GDB MAFWFBH MAFWRS MoFTER MPCERS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The OESCE project is in the implementation phase. The task of the project - helping BiH MoFTER to establish structures for the implementation of the Aarhus Convention. |
|  |  | MoFTER | Identify structures for implementation of the Espoo Convention | FMET GDB MAFWFBH MAFWRS MoFTER MPCERS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The activities aimed at establishing of structures are initiated jointly with competent entity institutions. |
| EP3.SP.158 | Implement strategic plans, including investment strategies, and increase investments in environmental infrastructure, with particular emphasis on waste water collection and treatment, drinking water supply and solid waste management | MoFTER | Set up and ensure functioning of units for preparation of infrastructural units | FMET GDB MAFWFBH MAFWRS MoFTER MPCERS | 1209 |  |  |  |  | Upon adoption of the Law on Environmental Protection in BiH, the Environmental Protection Sector will be established. Currently the BIH MoFTER Department for Environmental Protection has the total of 7 employees, of which 3 civil servants work on environmental protection programs and projects. The BiH MoFTER Natural Resources, Energy and Environment Sector, Department for Project Implementation employs 4 civil servants and is competent for preparation and implementation of projects aimed at environmental protection. There are also Units for Development of Infrastructure Projects in the F BiH and RS within their relevant ministries and institutions. There is no strategic plan for environmental protection at the BiH level. The F BiH has developed the strategy for 4 sectors, whereas it adopted the strategy for 3 sectors: air protection, nature protection and waste management; as for the water protection sector, the adoption procedure for the part of the strategy is ongoing. In the RS the strategy of air and nature protection is being developed. The Framework Plan for the Development of Water Management in the RS is adopted, and the development of the RS Strategy for Integrated Water Management is ongoing. The investment in infrastructure was increased.EU sredstva – IPA 2007/08/09 ukupno 20 mil Eura namijenjena uglavnom za otpadne vode i opskrbu pitkom vodom. Ostala sredstva za infrastrukturu su iz sredstava bilateralnih donatora. The EU funds - IPA 2007/08/09 of the total of 20 million Euros are intended mainly for wastewater and drinking water supply. Other sources for funding of infrastructure come from bilateral donors. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Energy |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.SP.163 | Accelerate the reform of energy utilities, in particular in the power and gas sectors, implement the Entities’ action plans for restructuring the power sector, develop and implement concomitant plans regarding reform of the coal sector, establish a transmission system operator and distribution system operators in the gas sector and develop the internal gas market | MoFTER | Draft and adopt BiH Law on Gas | FMEMI GDB MEEDRS MoFTER OPM PABH | 0610 |  |  |  |  | Implementation of the activity is postponed from 0609 to 0610. At the level of the Expert Team there is no agreement on establishment and competences of the institutions of the internal market in natural gas. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Transport policy |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.095 | Approximate to the road transport acquis (technical and safety standards, social rules and access to the market) | MCT | Implement the Rulebook on Technical Control of Vehicles (integrating the technical control points into the single information system) | FMCT GDB MCT MCTRS | 0909 |  |  |  |  | Implementation of the activity was postponed from 0609 to 0909. All stations for technical inspection of vehicles are connected into a single information system and as of September 28th 2009 the single concept of vehicle registration is applied. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Information society and media |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.099 | Implement and enforce the regulations on telecommunications/electronic communications aiming at a fully liberalised and competitive market. Introduce the necessary competitive safeguards in the market | MCT | Introduce the Mobile Virtual Network Operators - MVNO | CRA | 1210 | 100 | 50 | 50 |  | Implementation of the activity is postponed from 1208 to 1210. Drafting of the rules is ongoing and the implementation is expected in the course of 2010. |
|  |  | MCT | Market analysis | CRA | 1209 | 130 | 40 | 30 |  | Implementation of the activity was postponed from 1208 to 1209. The market analysis is within the CRA annual work report performed regularly for the sector of broadcasting and the sector of telecommunications.Izvještaj se ažurira krajem svake godine, i objavljuje na web stranici CRA. The report is updated at the end of each year, and published on the CRA website. |
| EP3.SP.165 | Fully implement public broadcasting legislation and complete the structural reform of the public broadcasting sector | MCT | Establish a System Committee - SC | MCT PABH | 0709 |  |  |  |  | Implementation of the activity was postponed from 0309 to 0709. The Steering Board of the RTV FBiH was constituted on July 6th 2009godine.. Ovim su imenovani svi članovi Odbora Sistema. All members of the System Board were thereby appointed. |
|  |  | MCT | Hold a constitutional session of the System Committee | MCT PABH | 0709 |  |  |  |  | Implementation of the activity was postponed from 0409 to 0709. The Constitutive Session of the System Board was held on August 11th 2009. |
|  |  | MCT | Adopt the Corporation Statute | MCT PABH | 0710 |  |  |  |  | Implementation of the activity is postponed from 1209 to 0710. The System Board planned to prepare the Working Draft of the Corporation Statute and the Action Plan for the establishment of the Corporation for the next session scheduled to take place onjanuar 2010. January 25th 2010.godine izraditi Radnu verziju Statuta Korporacije i Plana aktivnosti na uspostavi Korporacije. Odbor Sistema ima poteškoće oko donošenja Statuta jer zakon RTFBiH nije usklađen sa Zakonom o JRTS BiH. The System Board is facing difficulties in the process of the Statute adoption because the Law on RTV FBiH is not harmonized with the Law on PBS BiH. |
|  |  | MCT | Register the Corporation | MCT PABH | 0910 |  |  |  |  | Implementation of the activity is postponed from 0709 to 0910. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Financial control |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.101 | Develop and adopt a public internal financial control strategy | MFT | Adopt the Strategy for Implementation of Public Internal Financial Control (PIFC) in BiH | MFT | 0610 |  |  |  | IPA 2007 | Implementation of the activity is postponed from 0908 to 0610. The PIFC Strategy was adopted by the BiH Council of Ministers on December 30th 2009. The same strategy was developed for the entities (F BiH and RS), but it is in the process of adoption by the entity governments. |
| EP3.KP.102 | Adopt and implement legislation on public-sector internal control and audit | MFT | Make the Internal Audit Unit within BiH Ministry for Finance and Treasury operational | MFT | 1209 |  | 200 | 200 |  | Implementation of the activity was postponed from 0309 to 1209. Three vacancies were filled through the public competition procedure, i.e. chief internal auditor, senior internal auditor and internal auditor. TheKonkursna procedura okončana je 12.11.2009.g. competition procedure was completed on November 12th 2009. |
|  |  | MFT | Make Central Harmonization Unit operational and appoint Unit’s director | MFT | 0310 |  | 200 | 400 |  | Implementation of the activity is postponed from 0909 to 0310. The Council of Ministers adopted the Decision on Establishment of the Central Harmonization Unit, published in the Official Gazette of BiH No. 44/09.Direktor nije imenovan, očekuje se da se imenovanje završi do marta 2010.g. The Director has not been appointed, and the appointment is expected to be made by March 2010. |
|  |  | MFT | Integrate the Public Internal Financial Control system into the public administration and ensure its implementation | CoM | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The stated activity will be implemented in accordance with the adopted strategy and within the IPA technical assistance project. The Coordinating Board of the Central Harmonization Unit is the main collaborator of the technical assistance and the project manager. |
|  |  | MFT | Introduce common standards into internal control system, in compliance with the international standards | MFFBH MFRS MFT | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The stated activity will be implemented in accordance with the adopted strategy and within the IPA technical assistance project. |
|  |  | MFT | Set up an internal audit function in all BiH institutions in accordance with the adopted Internal Audit Law | MFFBH MFRS MFT | 1210 |  | 1000 | 2000 |  | Implementation of the activity is postponed from 1209 to 1210. Large budget users within the Institutions of BiH have planned the internal audit function within their organizational structure, but filling of the vacancies will be carried out once the Central Harmonization Unit has adopted the criteria. At the level of the institutions of the Federation, the 90% of internal audit divisions was established in accordance with the regulations adopted prior to adoption of the Law on Internal Audit. Internal auditors are employed regularly by the institutions of Republika Srpska in accordance with the requirements for establishing of the internal audit function defined by the Law on Internal Audit. |
| EP3.SP.168 | Implement the public internal financial control policy paper and action plan | MFT | Establish PIFC Central Harmonization and Control Units | MFFBH MFRS MFT | 0610 |  |  |  |  | Implementation of the activity is postponed from 1209 to 0610. The procedure of appointment of the head at the state level has not been completed, which caused delays of further activities. The appointment is expected to be made by March 2010. The Government of the Federation of BiH approved the Rulebook on Internal Organization of the FBiH MoF, stipulating the establishment of the Central Harmonization Unit Sector with two divisions. What follows is the procedure of filling of vacancies through public competition. The adopted Rulebook on Organization and Systematization of Working Posts of the RS MoF (Official Gazette of RS No. 108/09) defines the structure, responsibilities and competences of the CHU. The posts of the head of the CHU and the senior expert associate for information and communication are filled. Planning of the financial resources necessary for providing of premises, equipment, material costs and wages for the employment of the remaining staff of the CHU is ongoing. |
|  |  | MFT | Set up a Central Harmonization Units Coordination Committee | MFFBH MFRS MFT | 0610 |  |  |  |  | Implementation of the activity is postponed from 1209 to 0610. The procedure of appointment of the head has not been completed, which caused delays of further activities. The appointment is expected to be made by March 2010. |
| EP3.SP.170 | Develop procedures and administrative capacity to ensure effective protection of the EU’s financial interests | MFT | Establish principles, procedures and appropriate administrative capacities for introduction of Decentralised Implementation System (DIS) for managing the EU funds | DEI MFT | 0610 |  |  |  |  | Implementation of the activity is postponed from 1209 to 0610. The Central Financing and Contracting Unit (CFCU) and the National Fund (NF) are established and the principles and procedures (manuals) have been developed. The staff is trained. The Division for EU Integration is established in the MFT. U prvoj polovini 2010. In the first half of 2010 the appointments of Competent Accrediting Officersočekuje se imenovanje Službenika za akreditaciju (CAO), Državnog službenika za ovjeravanje (NAO) i imenovanje Voditelja programa/projekata (SPO-a) u okviru resornih ministarstava. (CAO), National Authorizing Officer (NAO) and Senior Program/Project Officers (SPO) are expected to be made in the line ministries. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Sectoral policies |  |  |  |  |  |  |  |  |  |
| Area: | Statistics |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.104 | Improve the collection and processing of agriculture statistics in line with EU standards and methodology | BHAS | Upgrade the ongoing researches in agricultural production statistics (plant and livestock production) in order to identify the insufficient categories of plants and livestock in accordance with the EU regulations | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The pilot study of farm structure was designed and it will be implemented in March 2010godine (uvedene su sve kategorije i vrste u skladu sa EU regulativama). (all categories and types were introduced in accordance with the EU regulations). It is planned toPlanirano je uključiti i sve nedostajuće kategorije bilja i stoke u redovna istraživanja (2011 g). include all missing categories of plants and livestock in regular research (2011). |
|  |  | BHAS | Participate in preparatory activities for agricultural census through implementation of IPA 2007 projects | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. Within the IPA 2007 regional project, the Country Report for BiH was produced (including the plans for agriculture census and research on farm structure). A special module of the so-called„filter pitanja“ iz oblasti poljoprivrede u sklopu upitnika za Popis stanovništva 2011. godine. "filter questions" from the area of agriculture is developed within the questionnaire for the 2011 Population Census. The implementation of the IPA 2007 project, which is implemented by the MoFTER, was initiated in December 2009 and the pilot agriculture census is expected to be conducted as a part of this project. |
| EP3.KP.105 | Improve the quality and coverage of statistics on consolidated government accounts | BHAS | Implement the activities from the multi-annual plan for development of national accounts | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The calculation of GDP by income approach was done for 2007 and 2008. A methodological improvement of GDP was effected by production approach, referring to the correct classification of taxes and subsidies in accordance with the ESA 95. The Multi-annual National Accounts (NA) Development Plan was not accepted by the RS Institute of Statistics in its part related to the establishment and development of statistics for the state level. |
|  |  | BHAS | Activities aimed at defining the state sector | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The sectorization of the BiH economy is planned within the IPA 2010 project, whose implementation has not yet started. |
| EP3.KP.106 | Establish the legislative framework necessary for carrying out the population census. Agree on a target date for the census and start preparations for implementing it | BHAS | Prepare a draft law on census and adopt it | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 0309 to 1210. The draft Law on Census of Population, Households and Dwellings was not passed in the first reading by the House of Representatives of the BiH Parliamentary Assembly at the session held on January 21st 2010. |
|  |  | BHAS | Successful implementation of IPA 2007 | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The IPA project was delayed and the implementation is expected to begin in late January 2010. |
|  |  | BHAS | Establish regular cooperation with all institutions involved in census-related activities | BHAS FZS RZSRS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. Cooperation with relevant institutions was realized in the preparation of the draft Law on Census, whereas concrete joint activities are expected to take place upon adoption of the Law. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Justice, freedom and security |  |  |  |  |  |  |  |  |  |
| Area: | Visa, border control, asylum and migration |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.107 | Provide adequate staffing for the migration section within the Ministry of Security and adequate facilities, equipment, staffing and training for the Department for Foreigners Affairs | MS | Establish and develop capacities for activities related to analysis and strategic planning in the field of immigration | CSA MS | 0809 |  |  |  |  | The position of the Expert Advisor for Analytics and Strategic Planning was filled (October 2009). The new Rulebook on Internal Organization and Systematization from September 24th 2009 stipulates a special organizational unit, the Office for Strategic Planning, Analysis and Statistics, in which two vacancies are filled. |
|  |  | MS | Strengthen capacities for monitoring of implementation and drafting of BiH legislation in the filed of immigration, implementation of readmission agreements in the part referring to readmission of BiH citizens, training, preparation and implementation of projects | CSA MS | 0809 |  |  |  |  | The position of the Senior Expert Advisor for Regulations was filled (October 2009). The Training Program in the area of immigration and asylum was developed (2009 - 2011), related to the implementation of the Law on Movement and Stay of Aliens and Asylum, as well as to its accompanying by-laws. Urađen Program obuke u oblasti imigracija i azila (2009. – 2011.) koji se odnosi na primjenu Zakona o kretanju i boravku stranaca i azilu kao i pratećih podzakonskih akata. In addition to the Sector for Immigration, which was the coordinator and organizer, participating in the preparation were also representatives of the Alien Affairs Service, the BiH Border Police, the MoS Sector for Asylum, and the Ministry of Foreign Affairs. |
|  |  | MS | Fill vacant positions in the Immigration Sector according to the new Rulebook | CSA MS | 0809 |  |  |  |  | The position of the Expert Advisor for Supervision of the Work of Centers for Accommodation of Aliens Victims of Human Trafficking was filled (October 2009). |
| EP3.KP.109 | Implement the EC/Bosnia and Herzegovina readmission agreement and negotiate readmission agreements with the countries of origin of transiting migrants | MS | Build the capacities of the Immigration Sector in terms of number of employees for the purpose of implementation of the Readmission Agreement in the part of BiH | CSA MS | 0809 |  |  |  |  | The competition procedure is ongoing for the position of the Expert Associate for Readmission Issues in the Sector for Immigration. The position is presently filled by the person hired based on the temporary service contract. |
| EP3.KP.110 | Ensure that reception centres meet international standards and assume full ownership of their financing and management | MS | Adopt by-laws regulating the functioning of the Asylum Centre | MS | 1209 |  |  |  |  | Implementation of the activity was postponed from 1208 to 1209. The BiH Council of Ministers adopted the Rulebook on Standards of Functioning and Other Issues Important for the Work of the Asylum Center at its 99th Sessionsjednici, održanoj 24. held on septembra 2009.September 24th 2009.godine, donijelo Pravilnik o standardima funkcionisanja i drugim pitanjima značajnim za rad azilantskog centra.Navedeni pravilnik stupio je na snagu danom donošenja i objavljen je u Sl. glasniku BiH, broj:86/09. The stated Rulebook entered into force on the date of its adoption and was published in the Official Gazette of BiH No. 86/09. |
|  |  | MS | Build the inspection capacities to monitor the application of the Council of Europe standards by asylum centres: regular reports, recommendations | MS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The Ministry of Security – Sector for Asylum made the proposal for amendment of the Rulebook on Internal Organization of the BIH MoS, whereby the position of the Senior Expert Associate for Monitoring and Reporting on Application of the Council of Europe Standards on Asylum Centers and Other Standards in the Area of International Protection was stipulated. The Sector for Asylum has also set up the Project of Capacity Development for Inspection of the Application of the Council of Europe Standards in Asylum Centers. The implementation is planned until the end of 2010. |
| EP3.KP.112 | Further improve border crossing points | MS | Designate institution for management of border crossings | CoM MS | 1209 |  |  |  |  | Implementation of the activity is postponed from 1008 to 1209. At its 94th Session held on July 16th 2009, the BiH Council of Ministers discussed the Information on the Management and Maintenance of Border Crossings in Bosnia and Herzegovina, submitted by the BiH State Commission for Integrated Border Management (the Commission), and adopted the conclusion whereby it accepted the decision to entrust the management and maintenance of border crossings to the BiH Indirect Taxation Authority (BiH ITA). The stated decision stipulates the adoption of the Proposal of the Rulebook on Amendments to the Rulebook on Internal Organization and Systematization of Working Posts in the BiH ITA, which will include working posts for management and maintenance. At the 9th Session of the Commission held on December 15th 2009, the Director of the BiH ITA reported that the new Proposal of the Amendments to the Rulebook on Internal Organization and Systematization of Working Posts was submitted to the Governing Board for adoption. The Proposal stipulates the systematization of the 70 new working posts instead of the 40 originally planned posts, with a view to adequately providing for the management and maintenance of all 89 border crossings in BiH. The ITA Director also reported that the ITA budget for 2010godinu, u kojem se predviđaju finansijska sredstva za tu namjenu, upućen Parlamentu BiH na usvajanje., which includes the financial resources planned for this purpose, was submitted to the BiH Parliament for adoption. |
| EP3.SP.172 | Further improve border management, with special emphasis on border infrastructure and surveillance of the green border | MS | Adopt necessary by-laws arising from the Law on Border Control | MS | 0310 |  |  |  |  | Implementation of the activity is postponed from 0309 to 0310. Of the planned 13 by-laws deriving from the Law on Border Control, 8 were drafted and adopted (1 was published in the Official Gazette, and the others are submitted for publication), 2 were submitted for adoption, 2 were drafted and sent to relevant institutions for opinion, whereas in the case of 1 by-law pertaining to border signs the regulation matter is not exclusively the competence of domestic institutions but is subject to agreements with neighboring states on bilateral basis, so that the further activities will be undertaken accordingly. The institution competent for preparation of this by-law is the Ministry of Civil Affairs, whereas its adoption is the competence of the Council of Ministers. |
|  |  | MS | Develop legal framework for establishment of a Joint Risk Analysis Centre for border security | MS | 1209 |  |  |  |  | The Agreement on Establishment of the Joint Risk Analysis Center was signed in December 2008godine, čime je definisan pravni okvir za funkcionisanje Centra.. It defined the legal framework for functioning of the Center. The Agreement was signed by the Minister of Security and Directors of Border Services Operating at Border Crossing Points. In March 2009godine, analitičari uključenih službi su upućen na rad u Zajedničkom centru koji je smješten pri Graničnoj policiji BiH. the analysts of the involved services were sent to work in the Joint Center, which is situated within the BiH Border Police. The Rulebook onPravilnik o radu centra je izrađen i usvojen. the Work of the Center was drafted and adopted. |
|  |  | MS | Adopt regulations for categorization of border crossings in order to decrease the number of international border crossings | MS | 0610 |  |  |  |  | Implementation of the activity is postponed from 1209 to 0610. The Rulebook on Standards and Requirements for Construction and Equipment of Border Crossings in BiH, which derives from the Law on Border Control, was adopted on December 30th 2009godine na 110. at the 110th Session of thesjednici Vijeća ministara. Predmetnim Pravilnikom se po prvi put reguliše pitanje jedinstvene standardizacije vezano za granične prelaze, kao i uslovi koji granični prelazi moraju ispunjavati u skladu sa dodijeljenom kategorijom. Council of Ministers. The stated Rulebook for the first time regulates the matter of uniform standardization related to border crossings, as well as conditions that border crossings must meet in accordance with their assigned category. However, the number and categories of border crossings are not exclusively the competence of BiH, but are decided through bilateral agreements with the neighboring states. BiH has signed and ratified agreements on the determination of border crossings with all the neighboring states. Currently there are ongoing activities to review these agreements, so that in December the revised Agreement on the Determination of Border Crossings and the revised Agreement on Border Traffic with the Republic of Montenegro were initialed, whereas the meeting with the Republic of Croatia was planned to take place in January with a view to starting the work on reviewing of the Agreement on the Determination of Border Crossings with Croatia. The initiative to review the Agreement with the Republic of Serbia was sent by BiH in June 2009godine, ali do sada nije dobijen oficijelni odgovor od Republike Srbije., but no official response was received from the Republic of Serbia to date. The revision of agreements on border crossings will regulate the number and categories of border crossings. |
|  |  | MS | Establish a wireless communication network across BiH (the owner of the network is the Ministry of Security and administrative structures within the Ministry) | BP MS | 1209 |  |  |  |  | In the course of 2009 all Field Offices, BP Units and 29 border crossings were linked by the SPIN communication network. 14 locations were linked by the SDH network, and there are presently no technical possibilities to increase the number of locations without the expansion of the basic infrastructure, which is the competence of the IDDEA. The ISM system is operational at 27 border crossings. |
|  |  | MS | Establish a system for exchange of data on misuse of travel documents and other documents within the organisational units of Border Police and with other law enforcement agencies | BP MS | 1210 |  |  |  |  | Implementation of the activity is postponed from 0908 to 1210. The BP regularly compiles, updates and distributes to lower-level organizational units the electronic collection of presentations of specimen and forged documents. In addition to the above stated, the alerts about newly discovered forms of document forging are regularly sent by e-mail internally to all of the BP organizational units. |
|  |  | MS | Establish an integrated system of border control at the international border crossings (Phase I) | BP MS | 1210 |  |  |  |  | Implementation of the activity is postponed from 1209 to 1210. The BP has established the Integrated System for Control of Crossing of the State Border (KPDG 2009) at 27 border crossings where the necessary infrastructural requirements (networking through SPIN and SDH network) were met, and the installation of travel document readers with accompanying computer equipment is ongoing therein. The stated Integrated System for Control of Crossing of the State Border (KPDG 2009) is integrated in the ISM as one of its modules (module "crossing of border"). The system allows the automatic recording of crossing of the state border and denial of entry to foreign nationals, with simultaneous checks in investigation databases including the MIND system for automatic control of the serial numbers of passports in the Interpol database of lost and stolen travel documents. The project is financed within the IPA program. The European Commission has invited tenders for procurement of hardware, and tenders were invited for development of the software as well.Sistem omogućava automatsko evidentiranje prelaska državne granice i odbijanje ulaska stranim državljanima, uz istovremene provjere u bazi potraga uključujući i MIND sistem za automatsku kontrolu serijskog broja putnih isprava u Interpol bazi podataka o izgubljenim i ukradenim putnim ispravama. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Justice, freedom and security |  |  |  |  |  |  |  |  |  |
| Area: | Money laundering |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.113 | Fully staff the Financial Intelligence Unit | MS | Fill the vacant positions of: Head and Deputy Head of Financial Intelligence Unit, Head of Department for Prevention and Investigation of Money Laundering and Terrorism Financing Crimes, five (5) inspectors in that Department, one (1) inspector in the Management Department, two (2) analysts, one (1) international cooperation advisor | MS SIPA | 1210 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. The position of the Deputy Head of the Financial Intelligence Department is filled and the public competition procedure for the position of the Head of the Department is ongoing. Also filled is the position of the Head of Department for Prevention and Investigation of Money Laundering and Financing of Terrorist Activities, so that at the end of 2009, 7 inspectors worked in the Department, which represents 58.33% of the number of systematized working posts in the Department. In the course of 2009, 3 analysts were employed in the Department for Analysis, so that the staffing of the Department reached 90% compared to the number of systematized working posts. The position of the Expert Adviser for International Cooperation is vacant as of December 1st 2009. The positions will be filled depending on the needs for human potential, budget allocations and accommodation capacity of the facilities. |
| EP3.KP.114 | Further improve legislation against money-laundering, including implementation and enforcement | MS | Draft and adopt amendments to the Rulebook on data, information and other minimum requirements for effective implementation of provisions of the Law Amending the Law on Prevention of Money Laundering | MS SIPA | 1209 |  |  |  |  | Implementation of the activity was postponed from 0209 to 1209. The Rulebook on Data, Information and Other Minimum Indicators Necessary for Effective Implementation of the Provisions of the Law on Preventing Money Laundering and Financing of Terrorist Activities was adopted and published in the Official Gazette of BiH No. 93/09 on December 1st 2009godine u Službenom glasniku BiH, broj 93/09.. |
|  |  | MS | Draft an Action Plan for Fight against Money Laundering | MS SIPA | 1009 |  |  |  |  | At its 100th Session held on September 30th 2009, the BiH Council of Ministers discussed and adopted the Strategy for Preventing Money Laundering and Financing of Terrorist Activities in Bosnia and Herzegovina. At the same time the Council of Ministers discussed and adopted the Action Plan for Preventing Money Laundering and Financing of Terrorist Activities in Bosnia and Herzegovina. |
| EP3.SP.173 | Ensure continued improvement of the enforcement record regarding money laundering | MS | Develop the phase IV of AMLS as follows: - development of security software for electronic registration of tax payers’ transactions at servers - upgrade of application module in already developed AMSL phases I, II and III | MS SIPA | 1210 |  |  |  |  | Implementation of the activity is postponed from 1208 to 1210. The upgrading (specific update of the AMLS software) of the existing phases I, II and III is in progress. The development of the phase II of the AMLS software is completed, the technical documentation is produced and user instructions prepared for officers of the Financial Intelligence Department. In the Financial Intelligence Department of the SIPA the AMLS phase III is completed along with the software “update”. The AMLS phase IV has not yet been initiated. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Justice, freedom and security |  |  |  |  |  |  |  |  |  |
| Area: | Drugs |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.115 | Develop a State level drugs policy in compliance with European standards | MS | Develop an Action Plan for implementation of the Strategy for Control, Prevention and Suppression of Narcotic Drugs Abuse | MIAFBH MIARS MS | 0909 |  |  |  |  | Implementation of the activity was postponed from 1208 to 0909. At its 99th Session held on September 24th 2009, the BiH Council of Ministers adopted the State Action Plan for Combating the Abuse of Illicit Drugs in BiH, which was proposed by the Ministry of Security. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Justice, freedom and security |  |  |  |  |  |  |  |  |  |
| Area: | Police |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.117 | Further strengthen the State Investigation and Protection Agency, notably by completing recruitment of its staff | MS | Complete and amend the Staff Recruitment Plan of the State Investigation and Protection Agency for 2008 | MS SIPA | 0210 |  |  |  |  | Implementation of the activity was postponed from 0609 to 0210. SIPA will comply with the deadline and a 2010 time schedule of employment in the Agency for in accordance with the 2010 dynamics of employment planned pursuant to the Law on the budget of BiH institutions and 2010 international obligations of BiH, according to which, by the end of 2010, the Agency will be 83.53% staffed in comparison with the total number of positions under the Rulebook on Structure and Job Descriptions. |
|  |  | MS | Fill 185 vacant positions through competition and open announcement procedure | MS SIPA | 1210 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 12/10. Bearing in mind the planned percentage of staffing by the end of 2010 (83.53%) and the level of staffing at the end of 2009r (69.98%), the Agency plans to hire 266 more employees in positions of civil servants, police officers and employees by the end of 2010. |
|  |  | MS | Recruit 100 cadets (70 holding the rank of policemen and 30 junior inspectors) | MS SIPA | 0810 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 08/10.The repeated procedure of selection of 20 police academy students - cadets who will have the rank of inspector junior following publication of vacancies on 30 August 2008 is in the final stage. The Board of Appeals is currently reviewing complaints filed by police officers. Final decisions and completion of the procedure of selection are expected by the end of January 2010. Afterwards a Police Academy will be selected (the deadline is the end of March 2010). Training of selected candidates at the Police Academy will last four months (by the end of July 2010). |
| EP3.SP.175 | Fully implement police reform | MS | Implement the Law on Directorate for Coordination of Police Bodies and on Agencies for BiH Police Structure Support, including the Law on Independent and Supervisory BiH Police Structure Bodies | CoM MS PABH | 1210 |  |  |  |  | Implementation of the activity was postponed from 12/09 to 12/10. |

| Title: | European standards |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter: | Justice, freedom and security |  |  |  |  |  |  |  |  |  |
| Area: | Fighting organised crime and terrorism |  |  |  |  |  |  |  |  |  |
| CODE | DESCRIPTION OF PRIORITY | MAIN RESPONSIBLE INSTITUTION | ACTIVITIES (Measures) | Institution | Deadline | Budget (2008) | Budget (2009) | Budget (2010) | IPA/MIPD | RPM |
| EP3.KP.121 | Reinforce the fight against organised crime and international cooperation with law enforcement agencies | MS | Satisfy the requirements for implementation of the Strategic Agreement on Cooperation with the EUROPOL | MIAFBH MIARS MS | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. The strategic agreement with EUROPOL is continuously implemented. Currently, setting up secure communication lines between BiH and Europol is in progress, based on the March 2009 Memorandum of Understanding. The secure communication network will serve for information exchange between EUROPOL and the Office for Cooperation with Interpol, which is currently, temporarily, designated as a contact point for cooperation with EUROPOL. |
| EP3.KP.122 | Take additional measures to protect victims of trafficking and ensure adequate implementation of the witness protection legislation | MS | Finalise the recruitment of staff for the Witness Protection Department in accordance with the job classification in force | MS SIPA | 0610 |  |  |  |  | Implementation of the activity was postponed from 12/08 to 06/10. The Witness Protection Department is staffed 66% compared to the total number of positions under the Rulebook on Structure. |
|  |  | MS | Adopt the Law Amending BiH Witness Protection Law | MS SIPA | 1210 |  |  |  |  | Implementation of the activity was postponed from 06/09 to 12/10. In the reporting period the Draft Law on Witness Protection Program in Bosnia and Herzegovina was in the parliamentary procedure, but it was not adopted, so that the initiative for the adoption of the Law has been re-launched. |
| EP3.SP.176 | Achieve significant results against organised crime, all types of trafficking and terrorism and ensure proper prosecution | MS | Harmonise BiH legislation with relevant international documents in this field | MJ MS | 1209 |  |  |  |  | Both Houses of the Parliamentary Assembly adopted the Law on Amendments to the Criminal Code of BiH on 30 December 2009. |
|  |  | MS | Educate judicial and investigation bodies in data collection and criminal processing (through seminars, consultations and study visits). Educate and train staff in applying safe methods for identification of potential perpetrators of criminal offences | LSBD MIAFBH MIARS MJ MJFBH MJRS MS | 1209 |  |  |  |  | The activity is carried out continuously. |

| AKRONIMI | INSTITUCIJA | INSTITUTION |
| --- | --- | --- |
| AB | Akcioni odbor | Action Board |
| ACBD | Apelaciona komisija BD | Appellate Commision of BD |
| AFWDBD | Odjel za poljuprivred, šumarstvo i vodoprivredu Brčko Distrikta | Agriculture, Forestry and Water-managment Department of BD |
| AI | Ured za reviziju finansijskog poslovanja | Auditing Institution |
| AFS | Agencija za sigurnost hrane | Agency for Food Safety |
| AIBD | Upravni inspektor BD | Administrative Inspector of BD |
| AIS | Agencija za informaciono drustvo | Agency for Information Society |
| AoC | Skupština Kantona | Assembly of Canton |
| APC | Agencija za privataziju kantona | Agency for Privatization of Cantons |
| APFBH | Agencija za privatizaciju FBiH | Agency for Privatization of FBiH |
| APOS | Agencija za predškolsko, osnovno i srednje obrazovanje | Agency for Preschool, Primary and Secondary Education |
| BARS | Agencija za bankarstvo Republike Srpske | Banking Agency of Republic of Srpska |
| BATA | Institut za akreditiranje | Institute for Accreditation |
| BHAS | Agencija za statistiku | Statistics Agency |
| BHCDA | Direkcija za civilno zrakoplovstvo Bosne i Hercegovine | Directorate of Civil Aviation of Bosnia and Herzegovina |
| BHRT | Radio-televizija BiH | Radio-television of BiH |
| BP | Granična policija | Border Police |
| CBBH | Centralna banka | Central Bank |
| CBH | Sud BiH | Court of BiH |
| CCBH | Konkurencijsko vijeće Bosne i Hercegovine | Competition Council of Bosnia and Herzegovina |
| CCRA | Vijeće Regulatorne agencije za komunikacije | Council of Communications Regulatory Agency |
| CE | Komora preduzetnika | Chamber of entrepreneurs |
| CEC | Centralna izborna komisija | Central Election Commission |
| CIPS | Sistem za identifikaciju i zaštitu podataka građana | Citizen Identification Protection System |
| CoM | Vijeće ministara | Council of Ministers |
| CPCDPR | Komisija za imovinske zahtjeve raseljenih lica i izbjeglica | Comission for Property Claims of Displaced Persons and Refugees |
| CRA | Regulatorna agencija za komunikacije | Communications Regulatory Agency |
| CRDP | Komisija za izbjeglice i raseljena lica | Commission for Refugees and Dispaced Persons |
| CSA | Agencija za državnu službu | Civil Service Agency |
| CSAFBH | Agencija za državnu službu Federacije BiH | Civil Service Agency of Federation BiH |
| CSARS | Agencija za državnu upravu Republike Srpske | Civil Service Agency of Republic of Srpska |
| CTJPRS | Centar za obuku sudija i tužilaca RS | Centre for Training of Judges and Prosecutors |
| CWG | Konsultativna radna grupa | Consultative Working Group |
| DEF | Fond za razvoj i poduzetništvo | Development and Enterpreneurship Fund |
| DEI | Direkcija za evropske integracije | Directorate for European Integration |
| DEP | Direkcija za ekonomsko planiranje | Economic Policy Planning Agency |
| FBA | Agencija za bankarstvo Federacije BiH | Federal Banking Agency |
| FDBD | Odjel za finansije BD | Financial Department of BD |
| FIM | Zavod za mjeriteljstvo Federacije BiH | Federal Institute for metrology |
| FIPA | Agencija za promociju stranih investicija | Foreign Investment Promotion Agency |
| FMCS | Ministarstvo kulture i sporta Federacije BiH | Federal Ministry of Culture and Sport |
| FMCT | Ministarstvo komunikacija i transporta Federacije BiH | Federal Ministry of Communication and Transport |
| FMDEC | Ministarstvo razvoja poduzetništva i obrta Federacije BiH | Federal Ministry of Development Enterpreneurship and Craft |
| FMDPR | Ministarstvo raseljenih osoba i izbjeglica Federacije BiH | Federal Ministry of Displaced Persons and Refugees |
| FMEMI | Ministarstvo energije rudarstva i industrije Federacije BiH | Ministry of Energy Mining and Industry of FBIH |
| FMES | Ministarstvo obrazovanja i nauke Federacije BiH | Federal Ministry of Education and Science |
| FMET | Ministarstvo okoliša i turizma Federacije BiH | Federal Ministry of Environment and Tourism |
| FMH | Ministarstvo zdravstva Federacije BiH | Federal Ministry of Health |
| FMICWV | Ministarstvo za pitanja boraca i invalida odbrambeno-oslobodilačkog rata Federacije BiH | Federal Ministry for Issues Concerning War Veterans |
| FMLSP | Ministarstvo rada i socijalne politike Federacije BiH | Federal Ministry of Labour and Social Policy |
| FMT | Ministarstvo trgovine Federacije BiH | Federal Ministry of Trade |
| FTC | Spoljnotrgovinska komora BiH | Foreign Chamber of Commerce of BiH |
| FTV | Federalna Televizija | Federal Television |
| FZS | Federalni zavod za statistiku | Federal Bureau of Statistics |
| GB | Upravni odbor | Governing Board |
| GDB | Vlada Brčko Distrikta | Government of Brcko District |
| GFBH | Vlada Federacije BiH | Government of F BiH |
| GEA | Agencija za ravnopravnost polova | Gender Equality Agency |
| GoC | Vlada kantona | Government of Canton |
| GRS | Vlada Republike Srpske | Government of RS |
| GS | Generalni sekretarijat Vijeća ministara | Council of Ministers General Secretariat |
| GSBD | Generalni sekretarijat Vlade BD | Goverment of BD General Secretariat |
| GSFBH | Generalni sekretarijat Vlade FBiH | Goverment of FBiH General Secretariat |
| GSRS | Generalni sekretarijat Vlade RS | Goverment of RS General Secretariat |
| HEA | Agencija za razvoj visokog obrazovanja i osiguranje kvaliteta | Agency for Development of Higher Education and Quality Assurance |
| HJPC | Visoko sudsko i tužilačko vijeće | High Judicial and Prosecutorial Council |
| HRUBD | Odjel za ljudske resurse BD | Human Resources Unit of BD |
| IABH | Agencija za osiguranje BiH | Insurance Agency of BiH |
| IDBRS | Investicijsko-razvojna banka Republike Srpske | Investment Development Bank of Republik of Srpska |
| IIP | Institut za intelektualno vlasništvo | Institut for Intellectual Property |
| IM | Institut za mjeriteljstvo | Institut for Metrology |
| IOM | Međunarodna organizacija za migracije | International Organisation for Migration |
| IS | Institut za standarde | Institut for Standars |
| ISA | Informativno-sigurnosna agencija | Information Security Agency |
| ISO | Nezavisni operarator sistema | Independent System Operator |
| ITA | Uprava za indirektno oporezivanje | Indirect Tax Authority |
| ITUBD | Odjeljenje za informatiku BD | Information Technology Unit of BD |
| JEPCC | Zajednički elektroenergetski koordinacioni centar | Joint Electric Power Supply Coordination Centre |
| JPTC | Judges and Prosecutors Training Center | Centar za obuku sudaca i tuzitelja |
| LEA | Agencija za rad i zapošljavanje | Labour and Employment Agency |
| LSBD | Pravna služba BD | Legal Service BD |
| MAFWFBH | Ministarstvo poljoprivrede, vodoprivrede i šumarstva Federacije BiH | Ministry of Agriculture, Water management and Forestry of Federation BiH |
| MAFWRS | Ministarstvo poljoprivrede, vodoprivrede i šumarstva Republike Srpske | Ministry of Agriculture, Water management and Forestry of Republic of Srpska |
| MASGRS | Ministarstvo uprave i lokalne samouprave Republike Srpske | Ministry of Administration and Self-Goverment of Republic of Srpska |
| MCA | Ministarstvo civilnih poslova | Ministry of Civil Affairs |
| MCT | Ministarstvo komunikacija i transporta | Ministry of Communication and Transport |
| MCTRS | Ministartstvo komunikacija i Transporta Republike Srpske | Ministry of communication and Transport of Rebulic of Srpska |
| MECRS | Ministarstvo prosvete i kulture Republike Srpske | Ministry of Education and Culture of Republic of Srpska |
| MEEDRS | Ministarstvo privrede energetike i razvoja RS | Ministry of Economy, Energy and Development of Republic of Srpska |
| MFA | Ministarstvo inostranih poslova | Ministry of Foreign Affairs |
| MFC | Ministarstva finansija kantona | Ministries of Finances of Cantons |
| MFFBH | Ministarstvo finansija Federacije BiH | Ministry of Finances of Federation of BiH |
| MFRS | Ministarstvo finansija Republike Srpske | Ministry of Finances of Repubilka Srpska |
| MFT | Ministarstvo finansija i trezora | Ministry of Finances and Treasury |
| MHRR | Ministarstvo za ljudska prava i izbjeglice | Ministry for Human Rights and Refugees |
| MHSPRS | Ministarstvo zdravlja i socijalne zaštite Republike Srpske | Ministry of Health and Social Protection of Republic of Srpska |
| MIAFBH | Ministarstvo unutrašnjih poslova Federacije BiH | Ministry of Interior Affairs of FBIH |
| MIARS | Ministarstvo unutrašnjih poslova Republike Srpske | Ministry of Interior Affairs of Republic of Srpska |
| MJ | Ministarstvo pravde | Ministry of Justice |
| MJC | Ministarstva pravde kantona | Ministries of Justice of Cantons |
| MJFBH | Ministarstvo pravde Federacije BiH | Ministry of Justice of Federation of Bosnia and Herzegovina |
| MJRS | Ministarstvo pravde Republike Srpske | Ministry of Justice of Republica Srpska |
| MM | Opštinski načelnik | Municipal Mayor |
| MoD | Ministarsvo odbrane | Ministry of Defence |
| MoFTER | Ministarstvo vanjske trgovine i ekonomskih odnosa | Ministry of Foreign Trade and Economic Relations |
| MPCERS | Ministarstvo za prostorno uređenje, građevinarstvo i ekologiju Republike Srpske | Ministry of Space Planning, Construction and Ecology of Republik of Srpska |
| MPRTS | Uprava Javnog radio-televizijskog servisa | Management of Public Radio Television Service |
| MS | Ministarstvo sigurnosti | Ministry of Security |
| MSA | Agencija za nadzor nad tržištem BiH | Market Surveillance Agency |
| MSTRS | Ministarstvo nauke i tehnologije Republike Srpske | Ministry of Science and Technology of Republic of Srpska |
| MTTRS | Ministarstvo trgovine i turizma Republike Srpske | Ministry of Trade and Tourism of Republic of Srpska |
| MVLP | Ministarstvo rada i boračko-invalidske zaštite Republike Srpske | Ministry of Labour and Veteran Protection of Republic of Srpska |
| NFC | Nacionalno fiskalno vijeće | National Fiscal Council |
| OBH | Ombudsmen Bosne i Hercegovine | Ombudsman of BiH |
| OCCPFBH | Ured za konkurenciju i zaštitu potrošača u FBiH | Office for Competition and Consumer Protection in F BiH |
| OCCPRS | Kancelarija za konkurenciju i zaštitu potrošača u RS | Office for Competition and Consumer Protection in RS |
| OFBH | Ombudsmen Federacije Bosne i Hercegovine | Ombudsman of F BiH |
| OLA | Ured za zakonodavstvo | Office of Legal Affairs |
| OPM | Ured premijera | Office of Primeminister |
| ORS | Ombudsmen Republike Srpske | Ombudsman of RS |
| PABD | Policijska uprava BD | Police Administration of BD |
| PABH | Parlamentarna Skupština Bosne i Hercegovine | Parliamentary Assembly of Bosnia and Herzegovna |
| PAFBH | Parlamentarna Skupština Federacije BiH | Parliamentary Assembly of F BiH |
| PAHP | Dom naroda Parlamentarne skupštine | Parliamentary Assembly House of People |
| PAHR | Zastupnički dom Parlamentarne skupštine | House of Representatives of Parlamentary Assembly |
| PARCO | Ured koordinatora za javnu upravu | Public Administration Reform - Coordinator Office |
| PARS | Narodna Skupština Rebulike Srpske | Parliamentary Assembly of RS |
| PBH | Predsjedništvo Bosne i Hercegovine | Presidency of Bosnia and Herzegovina |
| PDPA | Agencija za zaštitu ličnih podataka | Personal Data protection Agency |
| PHPA | Ured za zaštitu zdravlja bilja | Plant Health Protection Administration |
| PPA | Agencija za javne nabavke | Public Procurement Agency |
| PPOBH | Tužilaštvo BiH | Public Prosecutor's Office of BiH |
| PRB | Ured za razmatranje žalbi | Procurement Review Body |
| PURS | Elektroprivreda Republike Srpske | Power Utility of Republic of Srpska |
| RBBH | Ured za reviziju finansijskog poslovanja Institucija BiH | Revision Buerau of BiH |
| RC | Rektorska konferencija BiH | Rector's Conference BH |
| RCEFBH | Regulatorna komisija za električnu energiju Federacije BiH | Regulatory Commission for Electricity in Federation BiH |
| RCERS | Regulatorna komisija za energetiku Republike Srpske | Regulatory Commission for Energy in Republic of Srpska |
| RF | Fond za povratak | Return Fund |
| RISMRS | Republički zavod za standardizaciju i metrologiju Republike Srpske | Republic Institute for Standards and Metrology of Republic of Srpska |
| RTRS | Radio-televizija Republike Srpske | Radio-television of RS |
| RZSRS | Republički zavod za statistiku Republike Srpske | Institute of Statistics of Republica Srpska |
| SASMED | Republička agencija za razvoj malih i srednjih preduzeća | State Agency for SME development |
| SBC | Državna komisija za granicu | State Border Commission |
| SCFBH | Komisija za vrijednosne papire Federacije BiH | Securities Commission of Federation BiH |
| SCRS | Komisija za hartije od vrijednosti Republike Srpske | Securities Commission of Republic of Srpska |
| SEPRA | Državna regulatorna komisija za električnu energiju | State Electric Power Regulatory Commission |
| SFA | Služba za odnose za strancima | Service for Foreigner Affairs |
| SIPA | Agencija za istrage i zaštitu | State Information and Protection Agency |
| TC-MOFTER | Tehnički komitet Ministarstva vanjske trgovine i ekonomskih odnosa | Technical Committee - Ministry of Foreign Trade and Economic Relations |
| TRANSCO | Prenosna kompanija | Transmission Company |
| UNDP | Program razvoja Ujedinjenih Naroda | United Nations Development Program |
| VOBH | Ured za veterinarstvo Bosne i Hercegovine | Veterinary Office of Bosnia and Herzegovina |

Rulebook on Plastic Materials and Objects Intended for Contact with Food, Rulebook on Labels of Authenticity and Labels of Geographic Origine, Rulebook on Labels of Traditional Reputation of Food, Rulebook on Release of N-nitrosamine and N-nitrosamine Substance Precursors from Elastomers or Rubber Nipples for Bottles and Dummies, Rulebook on Ceramic Objects Intended for Contact with Food, Rulebook on Materials and Objects Intended for Contact with Food, Rulebook on Materials and Objects Contatining Vinyl Chloride Monomer and are Intended for Contact with Food, Rulebook on Materials and Objects Made of Regenerated Cellulose Film and Intended for Contact with Food, Rulebook on Restriction of Use of Epoxy Derivatives in Materials and Objects Intended for Contact with Food, Rulebook on Standards for Placing on the Market of Eggs, Rulebook on Sugar, Rulebook on Natural Mineral and Natural Spring Waters, Rulebook on Table Waters, Rulebook on Health Safety of Drinking Water.

Decision on Granting of Authorization to Testing Laboratories in BiH for Testing, Control and Monitoring of the Presence of Genetically Modified Organisms in Food and Animal Feed, authorizing 4 testing laboratories (adopted at the 113th Session of the BiH Council of Ministers held on January 21st 2010 and is expected to be published in the Official Gazette of BiH).